## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Pearl Yard food truck park · Total $2,289,739
COST SUMMARY
Construction hard cost | 917159.73
FF&E | 51460.63
Design + construction contingency | 156732.23
Hard cost subtotal | 1125352.59
Soft costs | 169718.05
Impact & tap fees | 0
Developer fee | 52132.91
Financing (interest + fees) | 35683.45
Soft cost contingency | 8252.15
Soft cost subtotal | 265786.56
Land & acquisition | 898600
Total project cost | 2289739.15
BASIS
Location | San Antonio, TX (factor 0.790)
Gross building SF | —
Site acres | 1.00
Cost per acre | 2289739.15
Research data version | 2026.0c737c8255
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.0c737c8255), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Pearl Yard food truck park · Total $2,289,739
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Food truck park | Food truck park | 12 pads | 1125352.59 | 265786.56 | 898600 | 2289739.15 | 190811.5958 |  | within ($32,657–$326,571)
Total |  |  | 1125352.59 | 265786.56 | 898600 | 2289739.15

## Phases
FINISHES SOLUTIONS
Cost by Phase · Pearl Yard food truck park · Total $2,289,739
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 6 | 2027-06 | 3.9% | 1125352.59 | 265786.56 | 898600 | 2289739.15 | 1373843.49 | 21945.02
Total |  |  |  |  | 1125352.59 | 265786.56 | 898600 | 2289739.15

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Pearl Yard food truck park · Total $2,289,739
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Food truck park | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 42403.27
Food truck park | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 42403.27
Food truck park | Phase 1 | Construction | 05 00 00 | Metals |  |  |  | 25441.97
Food truck park | Phase 1 | Construction | 06 00 00 | Wood, Plastics & Composites |  |  |  | 8480.66
Food truck park | Phase 1 | Construction | 07 00 00 | Thermal & Moisture Protection |  |  |  | 8480.66
Food truck park | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 4240.32
Food truck park | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 8480.66
Food truck park | Phase 1 | Construction | 10 00 00 | Specialties |  |  |  | 8480.66
Food truck park | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 29682.29
Food truck park | Phase 1 | Construction | 32 00 00 | Exterior Improvements |  |  |  | 84806.55
Food truck park | Phase 1 | Construction | 33 00 00 | Utilities |  |  |  | 59364.58
Food truck park | Phase 1 | Construction | 26 00 00 | Truck pad (concrete, ~450 SF) with utility pedestal (power, water) and trenching (within baseline) | 12 | pad | 20408.0912 | 244897.09
Food truck park | Phase 1 | Construction | 22 00 00 | Restroom building (site-built or prefab, ~400–600 SF) (within baseline) | 1 | ea | 162958.6283 | 162958.63
Food truck park | Phase 1 | Construction | 13 00 00 | Shade structure / covered seating pavilion (within baseline) | 4000 | SF | 40.3272 | 161308.81
Food truck park | Phase 1 | Specialty & site | 22 00 00 | Shared grease interceptor / grease disposal station (~1,000 gal) | 1 | ea | 25730.3136 | 25730.31
Food truck park | Phase 1 | FF&E | 12 00 00 | Furniture, fixtures & equipment | 12 | pad | 4288.3856 | 51460.63
Food truck park | Phase 1 | Contingency | 99 02 00 | Design contingency | 8 | % of hard |  | 73372.78
Food truck park | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 8 | % of hard |  | 83359.45
Food truck park | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 7.28 | % of hard |  | 70477.97
Food truck park | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 1.12 | % of hard |  | 10842.76
Food truck park | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 1.12 | % of hard |  | 10842.76
Food truck park | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.78 | % of hard |  | 7589.94
Food truck park | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.45 | % of hard |  | 4337.11
Food truck park | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.34 | % of hard |  | 3252.83
Food truck park | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.9 | % of hard |  | 8674.21
Food truck park | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.45 | % of hard |  | 4337.11
Food truck park | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.9 | % of hard |  | 8674.21
Food truck park | Phase 1 | Soft costs | SC | Owner's representative / project management | 1.68 | % of hard |  | 16264.15
Food truck park | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 19750 | 19750
Food truck park | Phase 1 | Contingency | SC | Soft cost contingency | 5 | % of soft |  | 8252.15
Food truck park | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 850000
Food truck park | Phase 1 | Land | LAND | Land closing costs |  |  |  | 17000
Food truck park | Phase 1 | Land | LAND | Land due diligence |  |  |  | 31600
Food truck park | Phase 1 | Soft costs | SC | Real estate taxes during construction | 0.5 | years | 9350 | 4675
Food truck park | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 52132.91
Food truck park | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 21945.02
Food truck park | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 13738.43
TOTAL |  |  |  | Total project cost |  |  |  | 2289739.15

## Draws
FINISHES SOLUTIONS
Draw Schedules · Pearl Yard food truck park · Total $2,289,739
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 104323.57 | 898600 | 915895.66 | 100766.34 | 0 | 100766.34
2027-04 | 75384.36 | 20963.27 | 0 | 0 | 96347.63 | 587.8 | 197701.77
2027-05 | 205953.79 | 20963.25 | 0 | 0 | 226917.04 | 1153.26 | 425772.07
2027-06 | 281338.15 | 20963.27 | 0 | 0 | 302301.42 | 2483.67 | 730557.16
2027-07 | 281338.12 | 20963.24 | 0 | 0 | 302301.36 | 4261.58 | 1037120.1
2027-08 | 205953.84 | 20963.3 | 0 | 0 | 226917.14 | 6049.87 | 1270087.11
2027-09 | 75384.33 | 20963.21 | 0 | 0 | 96347.54 | 7408.84 | 1373843.49

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Pearl Yard food truck park · Total $2,289,739
ASSUMPTIONS
Food truck park — baseline price | $97,971 / pad · Derived estimate — verify (entertainment/food-truck-park.json)
Food truck park — factors | regional 0.79 · quality 1 · size 0.9855 · escalation 1.0386
Food truck park — research note | Cost is driven by fixed shared amenities (restroom building, shade pavilion, seating plaza, lighting, grease handling) spread over a small number of truck pads, so cost per pad falls steeply with pad count. Public data are thin: a few municipal budgets/bids (Moses Lake WA, Albert Lea MN, Tyrone GA, North Summit UT) and Texas TDLR project registrations give a wide $30k–$200k+/pad spread; the mid is a reasoned build-up and should be verified.
Phase 1 — schedule | 2027-03, 6 months, midpoint 2027-06, escalation 3.86% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (39)
Ref | Source | Publisher | Value | Confidence | URL
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
entertainment/food-truck-park.json#e1 | Moses Lake Scraps Food Truck Park Project Amid Rising Costs, City Manager Confirms | Source ONE News | 598000 USD/ls (2023) | medium | https://www.yoursourceone.com/columbia_basin/moses-lake-scraps-food-truck-park-project-amid-rising-costs-city-manager-confirms/article_2e89da62-c7b2-47dc-8ca6-6cd778494c26.html
entertainment/food-truck-park.json#e2 | Albert Lea City Council gives green light for food truck court | KAAL ABC 6 News | 92693 USD/ls (2023) | medium | https://www.kaaltv.com/news/local-news/albert-lea-city-council-gives-green-light-for-food-truck-court/
entertainment/food-truck-park.json#e3 | Addendum Number 1, Design-Build Food Truck Park, Project Number DDA-2025-01 | Downtown Development Authority of Tyrone / Town of Tyrone, GA | 150000 USD/ls (2025) | medium | https://tyronega.gov/sites/default/files/uploads/Admin/dda-2025-01_addendum_number_1.pdf
entertainment/food-truck-park.json#e4 | Brothers plan to open $2.7M food truck park east of downtown by Fiesta | KSAT 12 | 2700000 USD/ls (2018) | low | https://www.ksat.com/news/2018/10/04/brothers-plan-to-open-27m-food-truck-park-east-of-downtown-by-fiesta/
entertainment/food-truck-park.json#e5 | North Summit Recreation SSD - Beacon Hill Park estimated costs for Food Truck Facilities and Basketball Courts (Restaurant Tax Grant packet) | Utah Public Notice Website / North Summit Recreation Special Service District | 18.86 USD/sf (2023) | medium | https://www.utah.gov/pmn/files/1031179.pdf
entertainment/food-truck-park.json#e6 | TABS2022015844 - Walsh Food Truck Pavilion | Texas Department of Licensing and Regulation (TABS) | 250000 USD/ls (2022) | medium | https://www.tdlr.texas.gov/TABS/Search/Print/TABS2022015844
entertainment/food-truck-park.json#e7 | TABS2026001089 - Vaquero Food Truck | Texas Department of Licensing and Regulation (TABS) | 180000 USD/ls (2025) | medium | https://www.tdlr.texas.gov/TABS/Search/Print/TABS2026001089
entertainment/food-truck-park.json#e8 | TABS2024016109 - Portable Restrooms, Food Truck Park | Texas Department of Licensing and Regulation (TABS) | 250000 USD/ls (2024) | medium | https://www.tdlr.texas.gov/TABS/Search/Print/TABS2024016109