## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Ashburn Campus — 24 MW data center · Total $493,631,983
COST SUMMARY
Construction hard cost | 334740685.98
FF&E | 0
Design + construction contingency | 44855251.92
Hard cost subtotal | 379595937.9
Soft costs | 40991382.32
Impact & tap fees | 1707684.48
Developer fee | 17025885.2
Financing (interest + fees) | 20318967.67
Soft cost contingency | 3352125.34
Soft cost subtotal | 83396045.01
Land & acquisition | 30640000
Total project cost | 493631982.91
BASIS
Location | Arlington, VA (factor 1.000)
Gross building SF | 288,000
Site acres | 16.00
Cost per acre | 30851998.9319
Research data version | 2026.0c737c8255
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.0c737c8255), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Ashburn Campus — 24 MW data center · Total $493,631,983
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Data hall building 1 | Data center | 24000 kW | 379595937.9 | 83396045.01 | 30640000 | 493631982.91 | 20567.9993 | 1713.9999 | within ($9,500–$24,000)
Total |  |  | 379595937.9 | 83396045.01 | 30640000 | 493631982.91

## Phases
FINISHES SOLUTIONS
Cost by Phase · Ashburn Campus — 24 MW data center · Total $493,631,983
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 29 | 2028-06 | 8.0% | 379595937.9 | 83396045.01 | 30640000 | 493631982.91 | 296179189.75 | 17357175.77
Total |  |  |  |  | 379595937.9 | 83396045.01 | 30640000 | 493631982.91

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Ashburn Campus — 24 MW data center · Total $493,631,983
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Data hall building 1 | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 7581295.52
Data hall building 1 | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 6317746.26
Data hall building 1 | Phase 1 | Construction | 05 00 00 | Metals |  |  |  | 5054197.01
Data hall building 1 | Phase 1 | Construction | 07 00 00 | Thermal & Moisture Protection |  |  |  | 2527098.51
Data hall building 1 | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 1263549.25
Data hall building 1 | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 1263549.25
Data hall building 1 | Phase 1 | Construction | 21 00 00 | Fire Suppression |  |  |  | 2527098.51
Data hall building 1 | Phase 1 | Construction | 22 00 00 | Plumbing |  |  |  | 1263549.25
Data hall building 1 | Phase 1 | Construction | 23 00 00 | HVAC |  |  |  | 31588731.32
Data hall building 1 | Phase 1 | Construction | 27 00 00 | Communications |  |  |  | 2527098.51
Data hall building 1 | Phase 1 | Construction | 28 00 00 | Electronic Safety & Security |  |  |  | 2527098.51
Data hall building 1 | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 2527098.51
Data hall building 1 | Phase 1 | Construction | 32 00 00 | Exterior Improvements |  |  |  | 2527098.51
Data hall building 1 | Phase 1 | Construction | 33 00 00 | Utilities |  |  |  | 1263549.25
Data hall building 1 | Phase 1 | Construction | 26 00 00 | Data-center MEP (electrical + mechanical infrastructure) (within baseline) | 24000 | kW | 8641.1352 | 207387244.86
Data hall building 1 | Phase 1 | Construction | 48 00 00 | Standby diesel generators (N+1 ≈ 1.25 kW per kW IT incl. mechanical load share) (within baseline) | 30000 | kW | 1022.3759 | 30671277.34
Data hall building 1 | Phase 1 | Construction | 26 00 00 | UPS modules, batteries and bypass (per kW IT) (within baseline) | 24000 | kW | 1080.1419 | 25923405.61
Data hall building 1 | Phase 1 | Contingency | 99 02 00 | Design contingency | 5 | % of hard |  | 16737034.3
Data hall building 1 | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 8 | % of hard |  | 28118217.62
Data hall building 1 | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 5.82 | % of hard |  | 19484905.6
Data hall building 1 | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 0.9 | % of hard |  | 2997677.79
Data hall building 1 | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 0.9 | % of hard |  | 2997677.78
Data hall building 1 | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.63 | % of hard |  | 2098374.45
Data hall building 1 | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.36 | % of hard |  | 1199071.11
Data hall building 1 | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.27 | % of hard |  | 899303.34
Data hall building 1 | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.72 | % of hard |  | 2398142.23
Data hall building 1 | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.36 | % of hard |  | 1199071.11
Data hall building 1 | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.72 | % of hard |  | 2398142.23
Data hall building 1 | Phase 1 | Soft costs | SC | Owner's representative / project management | 1.34 | % of hard |  | 4496516.68
Data hall building 1 | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 25000 | 25000
Data hall building 1 | Phase 1 | Impact & tap fees | SC | Total impact fees — industrial | 288 | 1,000 SF | 4225.85 | 1217044.8
Data hall building 1 | Phase 1 | Impact & tap fees | SC | Water capacity / tap / impact fee | 72 | EDU | 3407.22 | 245319.84
Data hall building 1 | Phase 1 | Impact & tap fees | SC | Sewer (wastewater) capacity / tap / impact fee | 72 | EDU | 3407.22 | 245319.84
Data hall building 1 | Phase 1 | Contingency | SC | Soft cost contingency | 8 | % of soft |  | 3352125.34
Data hall building 1 | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 30000000
Data hall building 1 | Phase 1 | Land | LAND | Land closing costs |  |  |  | 600000
Data hall building 1 | Phase 1 | Land | LAND | Land due diligence |  |  |  | 40000
Data hall building 1 | Phase 1 | Soft costs | SC | Real estate taxes during construction | 2.42 | years | 330000 | 797500
Data hall building 1 | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 17025885.2
Data hall building 1 | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 17357175.77
Data hall building 1 | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 2961791.9
TOTAL |  |  |  | Total project cost |  |  |  | 493631982.91

## Draws
FINISHES SOLUTIONS
Draw Schedules · Ashburn Campus — 24 MW data center · Total $493,631,983
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 25114571.2 | 30640000 | 58716363.1 | 0 | 0 | 0
2027-04 | 1112603.84 | 1309051.94 | 0 | 2421655.78 | 0 | 0 | 0
2027-05 | 3324767.22 | 1309051.94 | 0 | 4633819.16 | 0 | 0 | 0
2027-06 | 5497950.75 | 1309051.94 | 0 | 6807002.69 | 0 | 0 | 0
2027-07 | 7606675.83 | 1309051.94 | 0 | 8915727.77 | 0 | 0 | 0
2027-08 | 9626219.63 | 1309051.94 | 0 | 10935271.57 | 0 | 0 | 0
2027-09 | 11532904.76 | 1309051.94 | 0 | 12841956.7 | 0 | 0 | 0
2027-10 | 13304377.15 | 1309051.94 | 0 | 14613429.09 | 0 | 0 | 0
2027-11 | 14919867.82 | 1309051.94 | 0 | 16228919.76 | 0 | 0 | 0
2027-12 | 16360436.78 | 1309051.94 | 0 | 17669488.72 | 0 | 0 | 0
2028-01 | 17609194.51 | 1309051.94 | 0 | 18918246.45 | 0 | 0 | 0
2028-02 | 18651500.58 | 1309051.94 | 0 | 19960552.52 | 0 | 0 | 0
2028-03 | 19475134.85 | 1309051.94 | 0 | 4790359.85 | 15993826.94 | 0 | 15993826.94
2028-04 | 20070440.94 | 1309051.94 | 0 | 0 | 21379492.88 | 93297.32 | 37466617.14
2028-05 | 20430439.45 | 1309051.94 | 0 | 0 | 21739491.39 | 218555.27 | 59424663.8
2028-06 | 20550909.76 | 1309051.94 | 0 | 0 | 21859961.7 | 346643.87 | 81631269.37
2028-07 | 20430439.45 | 1309051.94 | 0 | 0 | 21739491.39 | 476182.4 | 103846943.16
2028-08 | 20070440.9 | 1309051.94 | 0 | 0 | 21379492.84 | 605773.84 | 125832209.84
2028-09 | 19475134.85 | 1309051.94 | 0 | 0 | 20784186.79 | 734021.22 | 147350417.85
2028-10 | 18651500.58 | 1309051.94 | 0 | 0 | 19960552.52 | 859544.1 | 168170514.47
2028-11 | 17609194.5 | 1309051.94 | 0 | 0 | 18918246.44 | 980994.67 | 188069755.58
2028-12 | 16360436.76 | 1309051.94 | 0 | 0 | 17669488.7 | 1097073.57 | 206836317.85
2029-01 | 14919867.81 | 1309051.94 | 0 | 0 | 16228919.75 | 1206545.19 | 224271782.79
2029-02 | 13304377.15 | 1309051.94 | 0 | 0 | 14613429.09 | 1308252.07 | 240193463.95
2029-03 | 11532904.76 | 1309051.94 | 0 | 0 | 12841956.7 | 1401128.54 | 254436549.19
2029-04 | 9626219.63 | 1309051.92 | 0 | 0 | 10935271.55 | 1484213.2 | 266856033.94
2029-05 | 7606675.83 | 1309051.94 | 0 | 0 | 8915727.77 | 1556660.2 | 277328421.91
2029-06 | 5497950.75 | 1309051.91 | 0 | 0 | 6807002.66 | 1617749.13 | 285753173.7
2029-07 | 3324767.22 | 1309051.94 | 0 | 0 | 4633819.16 | 1666893.51 | 292053886.37
2029-08 | 1112603.84 | 1309051.87 | 0 | 0 | 2421655.71 | 1703647.67 | 296179189.75

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Ashburn Campus — 24 MW data center · Total $493,631,983
ASSUMPTIONS
Data hall building 1 — baseline price | $12,000 / kW · Researched (industrial/data-center.json)
Data hall building 1 — factors | regional 1 · quality 1 · size 1.0761 · escalation 1.0801
Data hall building 1 — research note | Colocation/hyperscale data centers are priced per kW of critical IT load; 70–85% of construction cost is electrical (switchgear, UPS, generators, distribution) and mechanical (cooling) infrastructure, so cost tracks IT capacity rather than floor area. Evidence is good: Turner & Townsend (US$13.28/W Chicago, 2026), JLL ($11.3M/MW shell-and-core, 2026) and Cushman & Wakefield ($17.6M/MW all-in, 2026) agree once scope differences (land, sitework, soft costs, contingency) are reconciled. Liquid-cooled AI halls carry a 7–10% premium; IT equipment is excluded.
Phase 1 — schedule | 2027-03, 29 months, midpoint 2028-06, escalation 8.01% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (50)
Ref | Source | Publisher | Value | Confidence | URL
_blocks/specialty-mep.json#e10 | Data center construction input costs rise significantly | ConstructConnect | 0.7–0.87 pct (2025) | medium | https://news.constructconnect.com/data-center-construction-input-costs-rise-significantly
_blocks/specialty-mep.json#e11 | Permissible Uses of Energy Allocation Initiative Funding | New Jersey Office of Emergency Management | 450–650 USD/kw (2014) | medium | https://nj.gov/njoem/programs/pdf/hmgp/062414_hmgp_permlist.pdf
_blocks/specialty-mep.json#e12 | Microgrid Backbone Generation Assets, Part 1: Gen-Sets | CleanTechnica (Riverview Consulting) | 300–600 USD/kw (2012) | low | https://cleantechnica.com/2012/12/13/microgrid-backbone-generation-assets-part-1-gen-sets/
_blocks/specialty-mep.json#e6 | Data Centre Costs Explained | Datacentres.com | 2000000–4000000 USD/mw (2026) | medium | https://www.datacentres.com/guides/data-centre-costs-explained
_blocks/specialty-mep.json#e7 | Data Centre Costs Explained | Datacentres.com | 3000000–5000000 USD/mw (2026) | medium | https://www.datacentres.com/guides/data-centre-costs-explained
_blocks/specialty-mep.json#e8 | AI data centre rush raises alarm over construction supply chain | Turner & Townsend | 13300 USD/kw (2025) | high | https://www.turnerandtownsend.com/news/ai-data-centre-rush-raises-alarm-over-construction-supply-chain
_common/fees.json#e1 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 13627 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e2 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 6460 USD/unit (2019) | medium | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e6 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 3942 USD/1000sf (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
industrial/data-center.json#e1 | Data Center Development Cost Guide (2026) | Cushman & Wakefield | 17600 USD/kw (2026) | high | https://www.cushmanwakefield.com/en/united-states/insights/data-center-development-cost-guide
industrial/data-center.json#e10 | Data Centre Construction Costs Rise to $11.3M per MW in 2026 | Datacentres.com | 1000–2000 USD/kw (2026) | medium | https://www.datacentres.com/news/data-centre-construction-costs-11m-per-mw
industrial/data-center.json#e2 | Data Center Construction Costs Jump 21% Since 2024 | CRE Daily | 8900–23300 USD/kw (2026) | medium | https://www.credaily.com/?p=222025
industrial/data-center.json#e3 | Data Center Construction Costs Jump 21% Since 2024 | CRE Daily | 0.07–0.21 pct (2026) | medium | https://www.credaily.com/?p=222025
industrial/data-center.json#e4 | Data Center Outlook (2026 Global Data Center Outlook) | JLL | 11300 USD/kw (2026) | medium | https://www.jll.com/en-us/insights/market-outlook/data-center-outlook
industrial/data-center.json#e6 | Data centre construction cost index 2026 — Cost trends | Turner & Townsend | 13280 USD/kw (2026) | high | https://reports.turnerandtownsend.com/data-centre-construction-cost-index-2026/cost-trends
industrial/data-center.json#e7 | Data centre construction cost index 2026 — Methodology | Turner & Townsend | text (2026) | high | https://reports.turnerandtownsend.com/data-centre-construction-cost-index-2026/methodology
industrial/data-center.json#e8 | AI data center rush raises alarm over construction supply chain | Turner & Townsend | 13300 USD/kw (2025) | high | https://www.turnerandtownsend.com/en-us/news/ai-data-center-rush-raises-alarm-over-construction-supply-chain/
industrial/data-center.json#e9 | Data Centre Cost per MW by Region (October 2026 research update) | Next Move Strategy Consulting | 10000–14000 USD/kw (2026) | low | https://www.nextmsc.com/industry-deep-dive/data-centre-cost-per-mw-by-region
residential/single-family.json#e10 | Cost of Constructing a Home-2024 (Special Study for Housing Economics) | National Association of Home Builders (Eric Lynch) | 26747 USD/unit (2024) | high | https://nahb.org/-/media/AB4EFC742624475A97A0A62189986FF8.ashx