## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Hill Country event barn & retreat (Custom) · Total $9,381,122
COST SUMMARY
Construction hard cost | 5675760.77
FF&E | 0
Design + construction contingency | 730754.2
Hard cost subtotal | 6406514.97
Soft costs | 946588.39
Impact & tap fees | 0
Developer fee | 295981.38
Financing (interest + fees) | 224805.75
Soft cost contingency | 46431.09
Soft cost subtotal | 1513806.61
Land & acquisition | 1460800
Total project cost | 9381121.58
BASIS
Location | Texas (factor 0.820)
Gross building SF | —
Site acres | 18.00
Cost per acre | 521173.4211
Research data version | 2026.0c737c8255
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.0c737c8255), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Hill Country event barn & retreat (Custom) · Total $9,381,122
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Event barn & retreat | Custom (built from blocks) | 1 LS | 6406514.97 | 1513806.61 | 1460800 | 9381121.58 | 9381121.58 |  | within ($0–$1,000,000,000,000)
Total |  |  | 6406514.97 | 1513806.61 | 1460800 | 9381121.58

## Phases
FINISHES SOLUTIONS
Cost by Phase · Hill Country event barn & retreat (Custom) · Total $9,381,122
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 14 | 2027-10 | 5.2% | 6406514.97 | 1513806.61 | 1460800 | 9381121.58 | 5628672.95 | 168519.02
Total |  |  |  |  | 6406514.97 | 1513806.61 | 1460800 | 9381121.58

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Hill Country event barn & retreat (Custom) · Total $9,381,122
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Event barn & retreat | Phase 1 | Building blocks | 13 00 00 | Pre-engineered metal building (PEMB), erected and enclosed, light interior fit | 9000 | SF | 90.6 | 815400.39
Event barn & retreat | Phase 1 | Building blocks | 09 00 00 | Tenant improvement — standard (Gen 1 corporate office fit-out, hard cost) | 9000 | SF | 139.7829 | 1258046.32
Event barn & retreat | Phase 1 | Building blocks | 32 00 00 | Site development, typical commercial pad - all-in on-site (grading, utilities, paving, storm, lighting, landscaping) | 6 | acre | 224342.9644 | 1346057.79
Event barn & retreat | Phase 1 | Building blocks | 13 00 00 | Restroom building (prefab or site-built, park/amenity) | 900 | SF | 676.4717 | 608824.53
Event barn & retreat | Phase 1 | Building blocks | 13 00 00 | Pavilion / shade structure (open-sided roofed) | 3500 | SF | 70.4437 | 246552.92
Event barn & retreat | Phase 1 | Building blocks | 32 00 00 | Surface parking (asphalt, per space incl. drive aisles) | 180 | space | 5862.7547 | 1055295.84
Event barn & retreat | Phase 1 | Building blocks | 33 00 00 | Septic system, conventional (≈1,000-1,500 gal tank + gravity drainfield; small building) | 2 | ea | 17257.1511 | 34514.3
Event barn & retreat | Phase 1 | Building blocks | 33 00 00 | Water well, drilled (≈300-600 ft) with pump, pitless adapter, pressure tank - small non-community system | 1 | ea | 38828.59 | 38828.59
Event barn & retreat | Phase 1 | Building blocks | 11 00 00 | Commercial kitchen equipment package, installed (per SF of kitchen area) | 1200 | SF | 138.0572 | 165668.65
Event barn & retreat | Phase 1 | Building blocks | 10 00 00 | Monument sign (ground-mounted, masonry/aluminum base, illuminated) | 1 | ea | 21571.4389 | 21571.44
Event barn & retreat | Phase 1 | Building blocks | 01 00 00 | Owner-supplied lighting package | 1 | LS | 85000 | 85000
Event barn & retreat | Phase 1 | Contingency | 99 02 00 | Design contingency | 7.5 | % of hard |  | 425682.06
Event barn & retreat | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 5 | % of hard |  | 305072.14
Event barn & retreat | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 7.76 | % of hard |  | 440506.81
Event barn & retreat | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 1.19 | % of hard |  | 67770.28
Event barn & retreat | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 1.19 | % of hard |  | 67770.28
Event barn & retreat | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.84 | % of hard |  | 47439.19
Event barn & retreat | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.48 | % of hard |  | 27108.11
Event barn & retreat | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.36 | % of hard |  | 20331.08
Event barn & retreat | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.96 | % of hard |  | 54216.22
Event barn & retreat | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.48 | % of hard |  | 27108.11
Event barn & retreat | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.96 | % of hard |  | 54216.22
Event barn & retreat | Phase 1 | Soft costs | SC | Owner's representative / project management | 1.79 | % of hard |  | 101655.42
Event barn & retreat | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 20500 | 20500
Event barn & retreat | Phase 1 | Contingency | SC | Soft cost contingency | 5 | % of soft |  | 46431.09
Event barn & retreat | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 1400000
Event barn & retreat | Phase 1 | Land | LAND | Land closing costs |  |  |  | 28000
Event barn & retreat | Phase 1 | Land | LAND | Land due diligence |  |  |  | 32800
Event barn & retreat | Phase 1 | Soft costs | SC | Real estate taxes during construction | 1.17 | years | 15400 | 17966.67
Event barn & retreat | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 295981.38
Event barn & retreat | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 168519.02
Event barn & retreat | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 56286.73
TOTAL |  |  |  | Total project cost |  |  |  | 9381121.58

## Draws
FINISHES SOLUTIONS
Draw Schedules · Hill Country event barn & retreat (Custom) · Total $9,381,122
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 549108.17 | 1460800 | 2066194.9 | 0 | 0 | 0
2027-04 | 80312.34 | 52849.5 | 0 | 133161.84 | 0 | 0 | 0
2027-05 | 236909.86 | 52849.49 | 0 | 289759.35 | 0 | 0 | 0
2027-06 | 381627.72 | 52849.49 | 0 | 434477.21 | 0 | 0 | 0
2027-07 | 507209.18 | 52849.49 | 0 | 560058.67 | 0 | 0 | 0
2027-08 | 607357.04 | 52849.5 | 0 | 268796.66 | 391409.88 | 0 | 391409.88
2027-09 | 677049.5 | 52849.49 | 0 | 0 | 729898.99 | 2283.22 | 1123592.09
2027-10 | 712791.85 | 52849.5 | 0 | 0 | 765641.35 | 6554.29 | 1895787.73
2027-11 | 712791.86 | 52849.47 | 0 | 0 | 765641.33 | 11058.76 | 2672487.82
2027-12 | 677049.48 | 52849.52 | 0 | 0 | 729899 | 15589.51 | 3417976.33
2028-01 | 607357.04 | 52849.43 | 0 | 0 | 660206.47 | 19938.2 | 4098121
2028-02 | 507209.18 | 52849.43 | 0 | 0 | 560058.61 | 23905.71 | 4682085.32
2028-03 | 381627.71 | 52849.43 | 0 | 0 | 434477.14 | 27312.16 | 5143874.62
2028-04 | 236909.86 | 52849.52 | 0 | 0 | 289759.38 | 30005.94 | 5463639.94
2028-05 | 80312.35 | 52849.43 | 0 | 0 | 133161.78 | 31871.23 | 5628672.95

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Hill Country event barn & retreat (Custom) · Total $9,381,122
ASSUMPTIONS
Event barn & retreat — baseline price | $0 / LS · Derived estimate — verify (marine-other/custom.json)
Event barn & retreat — factors | regional 0.82 · quality 1 · size 1 · escalation 1.0523
Event barn & retreat — research note | A Custom component has no baseline price of its own: its hard cost is the sum of the building blocks the user adds (each priced from data/research/_blocks with its own sources) plus any hand-priced items. Soft costs, contingencies, fees and financing use the shared norms in data/research/_common.
Phase 1 — schedule | 2027-03, 14 months, midpoint 2027-10, escalation 5.23% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (52)
Ref | Source | Publisher | Value | Confidence | URL
_blocks/amenities.json#e13 | Legislation ID 26-23 — Large Park Restroom construction contract | City of Fresno | 608363 USD/ea (2025) | high | https://agendas.fresno.gov/en/legislation/id-26-23-20726
_blocks/amenities.json#e14 | Design, Manufacture, and Install a Prefabricated Restroom Building — City Council Regular Meeting (Dec 19, 2024) | City of Savannah, GA | 264927 USD/ea (2024) | high | https://agenda.savannahga.gov/publishing/december-19-2024-city-council-regular-meeting/1471_10896.html
_blocks/amenities.json#e23 | Pergola Cost | Fixr | 5700–30000 USD/ea (2022) | low | https://www.fixr.com/costs/build-pergola
_blocks/parking.json#e5 | Project Cost Sheet - Creation of E-1 Surface Parking Lot (Project 24134001) | University of Central Florida, Facilities Planning & Construction | 15505 USD/space (2025) | medium | https://fp.ucf.edu/wp-content/uploads/projects/costs/2026/24134001%20Creation%20of%20E-1%20Surface%20Parking%20Lot.pdf
_blocks/parking.json#e6 | The Costs of Parking in Hawai'i (August 2020) | Ulupono Initiative (cost estimates by Rider Levett Bucknall; land by PBR Hawaii) | 42000 USD/space (2020) | medium | https://www.ulupono.com/media/ivcfs2pu/the-cost-of-parking-in-hawaii-report-2020-08.pdf
_blocks/parking.json#e7 | How much does it cost to build a parking garage? | Fixr.com | 5000 USD/space (2022) | low | https://www.fixr.com/costs/build-parking-garage
_blocks/parking.json#e8 | WGI releases 2026 parking structure cost outlook | National Parking Association / Parking & Mobility (reporting WGI) | 31400 USD/space (2025) | high | https://www.parking-mobility.org/news/wgi-releases-2026-parking-structure-cost-outlook/
_blocks/paving.json#e1 | Item Average Unit Cost, From 2025/09/01 to 2026/08/31, Statewide (historical-item-averages-statewide-12-months) | Florida Department of Transportation | 136.23 USD/ton (2026) | high | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/fpo/fpc/reports/historicalitemaveragecost/moving/statewide/pdf/historical-item-averages-statewide-12-months.pdf?sfvrsn=32501f5b_15
_blocks/paving.json#e2 | Item Average Unit Cost, From 2025/09/01 to 2026/08/31, Statewide (historical-item-averages-statewide-12-months) | Florida Department of Transportation | 17.5 USD/sy (2026) | high | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/fpo/fpc/reports/historicalitemaveragecost/moving/statewide/pdf/historical-item-averages-statewide-12-months.pdf?sfvrsn=32501f5b_15
_blocks/paving.json#e4 | Item Average Unit Cost, From 2025/09/01 to 2026/08/31, Statewide (historical-item-averages-statewide-12-months) | Florida Department of Transportation | 38.56 USD/lf (2026) | high | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/fpo/fpc/reports/historicalitemaveragecost/moving/statewide/pdf/historical-item-averages-statewide-12-months.pdf?sfvrsn=32501f5b_15
_blocks/signage.json#e1 | Monument Signs for Businesses: A Complete Guide | AlphaGraphics Conroe | 5000–150000 USD/ea (2026) | low | https://www.alphagraphics.com/us-texas-conroe-us723/blog/blog-list/2026/07/monument-signs-for-businesses-a-complete-guide
_blocks/site-work.json#e3 | Item Average Unit Cost, From 2025/09/01 to 2026/08/31, Statewide (historical-item-averages-statewide-12-months) | Florida Department of Transportation | 6.81 USD/cy (2026) | high | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/fpo/fpc/reports/historicalitemaveragecost/moving/statewide/pdf/historical-item-averages-statewide-12-months.pdf?sfvrsn=32501f5b_15
_blocks/vertical-building.json#e1 | RLB Construction Cost Report North America Q3 2026 | Rider Levett Bucknall | 190–285 USD/sf (2026) | high | https://www.rlb.com/wp-content/uploads/sites/4/2026/09/Q3-2026-QCR.pdf
_blocks/vertical-building.json#e19 | Factory, 1 Story Construction Cost Model | Gordian RSMeans | 115.78 USD/sf (2019) | low | https://www.rsmeans.com/model-pages/factory-1-story
_blocks/vertical-building.json#e2 | RLB Construction Cost Report North America Q3 2026 | Rider Levett Bucknall | 195–285 USD/sf (2026) | high | https://www.rlb.com/wp-content/uploads/sites/4/2026/09/Q3-2026-QCR.pdf
_blocks/vertical-building.json#e20 | Office Fit Out Cost Guide 2026 (Americas) | Cushman & Wakefield | 162 USD/sf (2026) | high | https://digital.cushmanwakefield.com/fitoutcostguide-03-2026-amer-regional-en-content-pds-office/
_blocks/vertical-building.json#e21 | Office Fit Out Cost Guide 2026 (Americas) | Cushman & Wakefield | 196 USD/sf (2026) | high | https://digital.cushmanwakefield.com/fitoutcostguide-03-2026-amer-regional-en-content-pds-office/
_blocks/vertical-building.json#e23 | Office Fit Out Cost Guide 2026 ¦ US | Cushman & Wakefield | 108.26 USD/sf (2026) | high | https://www.cushmanwakefield.com/en/united-states/insights/office-fit-out-cost-guide
_blocks/vertical-building.json#e24 | Office Fit Out Cost Guide 2026 (Americas) | Cushman & Wakefield | 213.28 USD/sf (2026) | medium | https://digital.cushmanwakefield.com/fitoutcostguide-03-2026-amer-regional-en-content-pds-office/
_blocks/vertical-building.json#e3 | RLB Construction Cost Report North America Q3 2026 | Rider Levett Bucknall | 205–305 USD/sf (2026) | high | https://www.rlb.com/wp-content/uploads/sites/4/2026/09/Q3-2026-QCR.pdf
_blocks/vertical-building.json#e7 | RLB Construction Cost Report North America Q3 2026 | Rider Levett Bucknall | 155–245 USD/sf (2026) | high | https://www.rlb.com/wp-content/uploads/sites/4/2026/09/Q3-2026-QCR.pdf
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf