## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Prairie Sun — 50 MWdc solar farm · Total $76,697,263
COST SUMMARY
Construction hard cost | 59891773.54
FF&E | 0
Design + construction contingency | 4881179.55
Hard cost subtotal | 64772953.09
Soft costs | 4252111.65
Impact & tap fees | 0
Developer fee | 2777854.29
Financing (interest + fees) | 2145251.95
Soft cost contingency | 421292.42
Soft cost subtotal | 9596510.31
Land & acquisition | 2327800
Total project cost | 76697263.4
BASIS
Location | Texas (factor 0.820)
Gross building SF | —
Site acres | 250.00
Cost per acre | 306789.0536
Research data version | 2026.0c737c8255
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.0c737c8255), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Prairie Sun — 50 MWdc solar farm · Total $76,697,263
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Solar array | Solar farm (utility / community) | 50 MW | 64772953.09 | 9596510.31 | 2327800 | 76697263.4 | 1533945.268 |  | within ($925,284–$2,177,139)
Total |  |  | 64772953.09 | 9596510.31 | 2327800 | 76697263.4

## Phases
FINISHES SOLUTIONS
Cost by Phase · Prairie Sun — 50 MWdc solar farm · Total $76,697,263
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 19 | 2028-01 | 6.3% | 64772953.09 | 9596510.31 | 2327800 | 76697263.4 | 46018358.04 | 1685068.37
Total |  |  |  |  | 64772953.09 | 9596510.31 | 2327800 | 76697263.4

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Prairie Sun — 50 MWdc solar farm · Total $76,697,263
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Solar array | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 6991621.82
Solar array | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 443259.69
Solar array | Phase 1 | Construction | 25 00 00 | Integrated Automation |  |  |  | 196496.57
Solar array | Phase 1 | Construction | 26 00 00 | Electrical |  |  |  | 5108910.59
Solar array | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 1476009.05
Solar array | Phase 1 | Construction | 32 00 00 | Exterior Improvements |  |  |  | 1032749.36
Solar array | Phase 1 | Construction | 48 00 00 | Electrical Power Generation — balance |  |  |  | 13696232.93
Solar array | Phase 1 | Construction | 48 00 00 | PV module supply (bifacial mono) (within baseline) | 50 | MW | 364505.6665 | 18225283.33
Solar array | Phase 1 | Construction | 33 00 00 | Project substation & main power transformer (within baseline) | 1 | LS | 10344079.7497 | 10344079.75
Solar array | Phase 1 | Specialty & site | 33 00 00 | Generator tie / transmission line to POI | 5280 | LF | 450.2141 | 2377130.45
Solar array | Phase 1 | Contingency | 99 02 00 | Design contingency | 3 | % of hard |  | 1796753.21
Solar array | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 5 | % of hard |  | 3084426.34
Solar array | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 3.4 | % of hard |  | 2033638.58
Solar array | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 0.52 | % of hard |  | 312867.48
Solar array | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 0.52 | % of hard |  | 312867.47
Solar array | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.37 | % of hard |  | 219007.23
Solar array | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.21 | % of hard |  | 125146.99
Solar array | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.16 | % of hard |  | 93860.24
Solar array | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.42 | % of hard |  | 250293.98
Solar array | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.21 | % of hard |  | 125146.99
Solar array | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.42 | % of hard |  | 250293.98
Solar array | Phase 1 | Soft costs | SC | Owner's representative / project management | 0.78 | % of hard |  | 469301.21
Solar array | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 20500 | 20500
Solar array | Phase 1 | Contingency | SC | Soft cost contingency | 10 | % of soft |  | 421292.42
Solar array | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 2250000
Solar array | Phase 1 | Land | LAND | Land closing costs |  |  |  | 45000
Solar array | Phase 1 | Land | LAND | Land due diligence |  |  |  | 32800
Solar array | Phase 1 | Soft costs | SC | Real estate taxes during construction | 1.58 | years | 24750 | 39187.5
Solar array | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 2777854.29
Solar array | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 1685068.37
Solar array | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 460183.58
TOTAL |  |  |  | Total project cost |  |  |  | 76697263.4

## Draws
FINISHES SOLUTIONS
Draw Schedules · Prairie Sun — 50 MWdc solar farm · Total $76,697,263
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 2460866.3 | 2327800 | 5248849.88 | 0 | 0 | 0
2027-04 | 441709.33 | 262652.23 | 0 | 704361.56 | 0 | 0 | 0
2027-05 | 1313079.29 | 262652.23 | 0 | 1575731.52 | 0 | 0 | 0
2027-06 | 2148631.91 | 262652.22 | 0 | 2411284.13 | 0 | 0 | 0
2027-07 | 2925575.41 | 262652.22 | 0 | 3188227.63 | 0 | 0 | 0
2027-08 | 3622716.87 | 262652.22 | 0 | 3885369.09 | 0 | 0 | 0
2027-09 | 4221040.03 | 262652.21 | 0 | 4483692.24 | 0 | 0 | 0
2027-10 | 4704224.25 | 262652.21 | 0 | 4966876.46 | 0 | 0 | 0
2027-11 | 5059089.49 | 262652.21 | 0 | 4214512.85 | 1107228.85 | 0 | 1107228.85
2027-12 | 5275955.94 | 262652.21 | 0 | 0 | 5538608.15 | 6458.83 | 6652295.83
2028-01 | 5348908.06 | 262652.18 | 0 | 0 | 5611560.24 | 38805.06 | 12302661.13
2028-02 | 5275955.95 | 262652.25 | 0 | 0 | 5538608.2 | 71765.52 | 17913034.85
2028-03 | 5059089.49 | 262652.17 | 0 | 0 | 5321741.66 | 104492.7 | 23339269.21
2028-04 | 4704224.24 | 262652.25 | 0 | 0 | 4966876.49 | 136145.74 | 28442291.44
2028-05 | 4221040.02 | 262652.17 | 0 | 0 | 4483692.19 | 165913.37 | 33091897
2028-06 | 3622716.87 | 262652.25 | 0 | 0 | 3885369.12 | 193036.07 | 37170302.19
2028-07 | 2925575.41 | 262652.17 | 0 | 0 | 3188227.58 | 216826.76 | 40575356.53
2028-08 | 2148631.91 | 262652.25 | 0 | 0 | 2411284.16 | 236689.58 | 43223330.27
2028-09 | 1313079.31 | 262652.17 | 0 | 0 | 1575731.48 | 252136.09 | 45051197.84
2028-10 | 441709.31 | 262652.24 | 0 | 0 | 704361.55 | 262798.65 | 46018358.04

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Prairie Sun — 50 MWdc solar farm · Total $76,697,263
ASSUMPTIONS
Solar array — baseline price | $1,142,998 / MW · Researched (agriculture-energy/solar-farm.json)
Solar array — factors | regional 0.82 · quality 1 · size 1.057 · escalation 1.0626
Solar array — research note | Ground-mount single-axis-tracking PV priced per MWdc. Cost is dominated by modules, trackers/racking and electrical BOS. Scale economies are strong: LBNL finds projects over 250 MWac cost about 60% less per watt than projects under 20 MWac, so community-scale (1–20 MWac) projects sit at the high end. Data quality is high: an itemized Sargent & Lundy/EIA estimate, the DOE/NREL bottom-up benchmark and LBNL empirical plant data all agree within about 15%.
Phase 1 — schedule | 2027-03, 19 months, midpoint 2028-01, escalation 6.26% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (35)
Ref | Source | Publisher | Value | Confidence | URL
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
agriculture-energy/solar-farm.json#e1 | Capital Cost and Performance Characteristic Estimates for Utility Scale Electric Power Generating Technologies (Sargent & Lundy for EIA), Case 16 Solar PV with Single-Axis Tracking, 150 MWAC | U.S. Energy Information Administration / Sargent & Lundy | 1082487 USD/mw (2023) | high | https://www.eia.gov/analysis/studies/powerplants/capitalcost/pdf/capital_cost_AEO2025.pdf
agriculture-energy/solar-farm.json#e2 | Utility-Scale Solar, 2024 Edition — Executive Summary | Lawrence Berkeley National Laboratory | 1080000 USD/mw (2023) | high | https://eta-publications.lbl.gov/sites/default/files/2024-10/utility-scale_solar_2024_executive_summary.pdf
agriculture-energy/solar-farm.json#e3 | Solar Photovoltaic System Cost Benchmarks (2025Q1 benchmarks) | U.S. Department of Energy, Solar Energy Technologies Office (NREL modeling) | 1120000 USD/mw (2024) | high | https://www.energy.gov/eere/solar/solar-photovoltaic-system-cost-benchmarks
agriculture-energy/solar-farm.json#e4 | Cost of Utility-Scale Solar: LCOE, PPAs, and Storage (summarizing LBNL U.S. Utility-Scale Solar, 2025 Data Update slides) | LegalClarity (secondary, citing Lawrence Berkeley National Laboratory) | 1220000 USD/mw (2024) | medium | https://legalclarity.org/cost-of-utility-scale-solar-lcoe-ppas-and-storage/