## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Harbor Point — select-service hotel · Total $30,663,374
COST SUMMARY
Construction hard cost | 17213433.31
FF&E | 2336729.26
Design + construction contingency | 1881213.38
Hard cost subtotal | 21431375.95
Soft costs | 3205509.34
Impact & tap fees | 597530.72
Developer fee | 1016871.25
Financing (interest + fees) | 925921
Soft cost contingency | 187365.34
Soft cost subtotal | 5933197.65
Land & acquisition | 3298800
Total project cost | 30663373.6
BASIS
Location | Nashville, TN (factor 0.870)
Gross building SF | 76,880
Site acres | 2.48
Cost per acre | 12364263.5484
Research data version | 2026.7c60a42879
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.7c60a42879), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Harbor Point — select-service hotel · Total $30,663,374
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Harbor Point hotel | Select-service hotel | 124 keys | 21431375.95 | 5933197.65 | 3298800 | 30663373.6 | 247285.271 | 398.8472 | within ($146,345–$334,502)
Total |  |  | 21431375.95 | 5933197.65 | 3298800 | 30663373.6

## Phases
FINISHES SOLUTIONS
Cost by Phase · Harbor Point — select-service hotel · Total $30,663,374
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 19 | 2028-01 | 6.3% | 21431375.95 | 5933197.65 | 3298800 | 30663373.6 | 18398024.16 | 741940.76
Total |  |  |  |  | 21431375.95 | 5933197.65 | 3298800 | 30663373.6

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Harbor Point — select-service hotel · Total $30,663,374
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Harbor Point hotel | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 1333935.05
Harbor Point hotel | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 1000451.29
Harbor Point hotel | Phase 1 | Construction | 04 00 00 | Masonry |  |  |  | 333483.76
Harbor Point hotel | Phase 1 | Construction | 05 00 00 | Metals |  |  |  | 666967.53
Harbor Point hotel | Phase 1 | Construction | 06 00 00 | Wood, Plastics & Composites |  |  |  | 1834160.69
Harbor Point hotel | Phase 1 | Construction | 07 00 00 | Thermal & Moisture Protection |  |  |  | 1000451.29
Harbor Point hotel | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 833709.41
Harbor Point hotel | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 2000902.57
Harbor Point hotel | Phase 1 | Construction | 10 00 00 | Specialties — balance |  |  |  | 312537.94
Harbor Point hotel | Phase 1 | Construction | 11 00 00 | Equipment |  |  |  | 333483.76
Harbor Point hotel | Phase 1 | Construction | 12 00 00 | Furnishings |  |  |  | 333483.76
Harbor Point hotel | Phase 1 | Construction | 14 00 00 | Conveying Equipment |  |  |  | 333483.76
Harbor Point hotel | Phase 1 | Construction | 21 00 00 | Fire Suppression |  |  |  | 333483.76
Harbor Point hotel | Phase 1 | Construction | 22 00 00 | Plumbing |  |  |  | 1333935.05
Harbor Point hotel | Phase 1 | Construction | 23 00 00 | HVAC |  |  |  | 1167193.17
Harbor Point hotel | Phase 1 | Construction | 26 00 00 | Electrical |  |  |  | 1333935.05
Harbor Point hotel | Phase 1 | Construction | 27 00 00 | Communications |  |  |  | 333483.76
Harbor Point hotel | Phase 1 | Construction | 28 00 00 | Electronic Safety & Security |  |  |  | 166741.88
Harbor Point hotel | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 500225.64
Harbor Point hotel | Phase 1 | Construction | 32 00 00 | Exterior Improvements |  |  |  | 666967.52
Harbor Point hotel | Phase 1 | Construction | 33 00 00 | Utilities |  |  |  | 500225.64
Harbor Point hotel | Phase 1 | Construction | 10 00 00 | Brand monument sign (within baseline) | 1 | ea | 20945.821 | 20945.82
Harbor Point hotel | Phase 1 | Specialty & site | 01 00 00 | Pre-opening, OS&E and working capital | 124 | key | 4348.7517 | 539245.21
Harbor Point hotel | Phase 1 | FF&E | 12 00 00 | Furniture, fixtures & equipment | 124 | key | 18844.5908 | 2336729.26
Harbor Point hotel | Phase 1 | Contingency | 99 02 00 | Design contingency | 5 | % of hard |  | 860671.67
Harbor Point hotel | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 5 | % of hard |  | 1020541.71
Harbor Point hotel | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 7.76 | % of hard |  | 1517326.05
Harbor Point hotel | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 1.19 | % of hard |  | 233434.78
Harbor Point hotel | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 1.19 | % of hard |  | 233434.78
Harbor Point hotel | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.84 | % of hard |  | 163404.34
Harbor Point hotel | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.48 | % of hard |  | 93373.91
Harbor Point hotel | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.36 | % of hard |  | 70030.43
Harbor Point hotel | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.96 | % of hard |  | 186747.82
Harbor Point hotel | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.48 | % of hard |  | 93373.91
Harbor Point hotel | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.96 | % of hard |  | 186747.82
Harbor Point hotel | Phase 1 | Soft costs | SC | Owner's representative / project management | 1.79 | % of hard |  | 350152.17
Harbor Point hotel | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 21750 | 21750
Harbor Point hotel | Phase 1 | Impact & tap fees | SC | Total impact fees — hotel room | 124 | key | 3357.05 | 416274.2
Harbor Point hotel | Phase 1 | Impact & tap fees | SC | Water capacity / tap / impact fee | 19.22 | EDU | 4838.18 | 92989.82
Harbor Point hotel | Phase 1 | Impact & tap fees | SC | Sewer (wastewater) capacity / tap / impact fee | 19.22 | EDU | 4592.44 | 88266.7
Harbor Point hotel | Phase 1 | Contingency | SC | Soft cost contingency | 5 | % of soft |  | 187365.34
Harbor Point hotel | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 3200000
Harbor Point hotel | Phase 1 | Land | LAND | Land closing costs |  |  |  | 64000
Harbor Point hotel | Phase 1 | Land | LAND | Land due diligence |  |  |  | 34800
Harbor Point hotel | Phase 1 | Soft costs | SC | Real estate taxes during construction | 1.58 | years | 35200 | 55733.33
Harbor Point hotel | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 1016871.25
Harbor Point hotel | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 741940.76
Harbor Point hotel | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 183980.24
TOTAL |  |  |  | Total project cost |  |  |  | 30663373.6

## Draws
FINISHES SOLUTIONS
Draw Schedules · Harbor Point — select-service hotel · Total $30,663,374
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 2440071.98 | 3298800 | 5922852.22 | 0 | 0 | 0
2027-04 | 146148.01 | 135116.05 | 0 | 281264.06 | 0 | 0 | 0
2027-05 | 434457.47 | 135116.04 | 0 | 569573.51 | 0 | 0 | 0
2027-06 | 710916.15 | 135116.03 | 0 | 846032.18 | 0 | 0 | 0
2027-07 | 967982.85 | 135116.02 | 0 | 1103098.87 | 0 | 0 | 0
2027-08 | 1198645.46 | 135116.02 | 0 | 1333761.48 | 0 | 0 | 0
2027-09 | 1396612.2 | 135116.02 | 0 | 1531728.22 | 0 | 0 | 0
2027-10 | 1556482.97 | 135116.02 | 0 | 677038.9 | 1014560.09 | 0 | 1014560.09
2027-11 | 1673897.01 | 135116.02 | 0 | 0 | 1809013.03 | 5918.27 | 2829491.39
2027-12 | 1745651.4 | 135116.02 | 0 | 0 | 1880767.42 | 16505.37 | 4726764.18
2028-01 | 1769788.99 | 135116.02 | 0 | 0 | 1904905.01 | 27572.79 | 6659241.98
2028-02 | 1745651.42 | 135116.08 | 0 | 0 | 1880767.5 | 38845.58 | 8578855.06
2028-03 | 1673896.96 | 135116.02 | 0 | 0 | 1809012.98 | 50043.32 | 10437911.36
2028-04 | 1556482.96 | 135116.08 | 0 | 0 | 1691599.04 | 60887.82 | 12190398.22
2028-05 | 1396612.2 | 135116.01 | 0 | 0 | 1531728.21 | 71110.66 | 13793237.09
2028-06 | 1198645.46 | 135116.08 | 0 | 0 | 1333761.54 | 80460.55 | 15207459.18
2028-07 | 967982.79 | 135116.01 | 0 | 0 | 1103098.8 | 88710.18 | 16399268.16
2028-08 | 710916.14 | 135116.07 | 0 | 0 | 846032.21 | 95662.4 | 17340962.77
2028-09 | 434457.5 | 135115.99 | 0 | 0 | 569573.49 | 101155.62 | 18011691.88
2028-10 | 146148.01 | 135116.07 | 0 | 0 | 281264.08 | 105068.2 | 18398024.16

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Harbor Point — select-service hotel · Total $30,663,374
ASSUMPTIONS
Harbor Point hotel — baseline price | $146,345 / key · Researched (hospitality/hotel-select-service.json)
Harbor Point hotel — factors | regional 0.87 · quality 1 · size 0.994 · escalation 1.0626
Harbor Point hotel — research note | Branded 4–5 story select/limited-service hotel (Hampton / Courtyard class) of ~80–160 keys with breakfast area, small meeting room, fitness and pool; cost is driven by guestroom count, framing system (wood vs. concrete/steel) and market. Data quality is good: four editions of the HVS U.S. Hotel Development Cost Survey (2022–2025 data) give national per-key medians by component, cross-checked with RLB Q2 2026 3-star $/SF and an HVS feasibility budget. HVS building costs include permits, engineering and hard contingency, so they are scaled to our hard-cost definition.
Phase 1 — schedule | 2027-03, 19 months, midpoint 2028-01, escalation 6.26% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (57)
Ref | Source | Publisher | Value | Confidence | URL
_common/fees.json#e1 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 13627 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e2 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 6460 USD/unit (2019) | medium | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e3 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 8034 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e5 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 5408 USD/1000sf (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
hospitality/hotel-select-service.json#e1 | HVS U.S. Hotel Development Cost Survey 2026 | HVS | 126900 USD/key (2025) | high | https://www.hvs.com/article/10509-HVS-US-Hotel-Development-Cost-Survey-2026
hospitality/hotel-select-service.json#e11 | Hotel, 4-7 Story with Brick Veneer / Reinforced Concrete — square foot model | Gordian RSMeans | 197.45 USD/sf (2019) | medium | https://www.rsmeans.com/model-pages/hotel-4-7-story
hospitality/hotel-select-service.json#e12 | HVS U.S. Hotel Development Cost Survey 2026 | HVS | 18321 USD/key (2025) | high | https://www.hvs.com/article/10509-HVS-US-Hotel-Development-Cost-Survey-2026
hospitality/hotel-select-service.json#e13 | HVS U.S. Hotel Development Cost Survey 2026 | HVS | 16079 USD/key (2025) | high | https://www.hvs.com/article/10509-HVS-US-Hotel-Development-Cost-Survey-2026
hospitality/hotel-select-service.json#e14 | HVS U.S. Hotel Development Cost Survey 2025 | HVS | 22929 USD/key (2024) | high | https://www.hvs.com/article/10219-hvs-us-hotel-development-cost-survey-2025
hospitality/hotel-select-service.json#e15 | Feasibility Study — Proposed Limited-Service Hotel, Murrieta, California (May 2022) | HVS for City of Murrieta | 17000 USD/key (2022) | high | https://www.murrietaca.gov/DocumentCenter/View/7349/HVS-Feasibility-Study-2022---Proposed-Limited-Service-Hotel-PDF
hospitality/hotel-select-service.json#e16 | HVS U.S. Hotel Development Cost Survey 2026 | HVS | 21002 USD/key (2025) | high | https://www.hvs.com/article/10509-HVS-US-Hotel-Development-Cost-Survey-2026
hospitality/hotel-select-service.json#e17 | HVS U.S. Hotel Development Cost Survey 2026 | HVS | 19896 USD/key (2025) | high | https://www.hvs.com/article/10509-HVS-US-Hotel-Development-Cost-Survey-2026
hospitality/hotel-select-service.json#e18 | HVS U.S. Hotel Development Cost Survey 2025 | HVS | 24833 USD/key (2024) | high | https://www.hvs.com/article/10219-hvs-us-hotel-development-cost-survey-2025
hospitality/hotel-select-service.json#e19 | Feasibility Study — Proposed Limited-Service Hotel, Murrieta, California (May 2022) | HVS for City of Murrieta | 30000 USD/key (2022) | high | https://www.murrietaca.gov/DocumentCenter/View/7349/HVS-Feasibility-Study-2022---Proposed-Limited-Service-Hotel-PDF
hospitality/hotel-select-service.json#e2 | HVS U.S. Hotel Development Cost Survey 2026 | HVS | 141143 USD/key (2025) | high | https://www.hvs.com/article/10509-HVS-US-Hotel-Development-Cost-Survey-2026
hospitality/hotel-select-service.json#e20 | HVS U.S. Hotel Development Cost Survey 2026 | HVS | 3561 USD/key (2025) | high | https://www.hvs.com/article/10509-HVS-US-Hotel-Development-Cost-Survey-2026
hospitality/hotel-select-service.json#e21 | HVS U.S. Hotel Development Cost Survey 2026 | HVS | 2900 USD/key (2025) | high | https://www.hvs.com/article/10509-HVS-US-Hotel-Development-Cost-Survey-2026
hospitality/hotel-select-service.json#e22 | HVS U.S. Hotel Development Cost Survey 2025 | HVS | 5894 USD/key (2024) | high | https://www.hvs.com/article/10219-hvs-us-hotel-development-cost-survey-2025
hospitality/hotel-select-service.json#e23 | Feasibility Study — Proposed Limited-Service Hotel, Murrieta, California (May 2022) | HVS for City of Murrieta | 4000 USD/key (2022) | high | https://www.murrietaca.gov/DocumentCenter/View/7349/HVS-Feasibility-Study-2022---Proposed-Limited-Service-Hotel-PDF
hospitality/hotel-select-service.json#e3 | HVS U.S. Hotel Development Cost Survey 2025 | HVS | 159636 USD/key (2024) | high | https://www.hvs.com/article/10219-hvs-us-hotel-development-cost-survey-2025
hospitality/hotel-select-service.json#e31 | Hotel Cost Estimating Guide 2021 | Nehmer and HVS Design | 11948–17563 USD/ea (2021) | medium | https://www.hvs.com/WebContent/bookstore/HVS%20Hotel%20Cost%20Estimating%20Guide%202021.pdf
hospitality/hotel-select-service.json#e4 | HVS U.S. Hotel Development Cost Survey 2025 | HVS | 111846 USD/key (2024) | high | https://www.hvs.com/article/10219-hvs-us-hotel-development-cost-survey-2025
hospitality/hotel-select-service.json#e5 | HVS U.S. Hotel Development Cost Survey 2024 | HVS | 161216 USD/key (2023) | high | https://www.hvs.com/article/9999-hvs-us-hotel-development-cost-survey-2024
hospitality/hotel-select-service.json#e6 | HVS U.S. Hotel Development Cost Survey 2023 | HVS | 161853 USD/key (2022) | high | https://www.hvs.com/article/9704-hvs-us-hotel-development-cost-survey-2023
hospitality/hotel-select-service.json#e7 | Feasibility Study — Proposed Limited-Service Hotel, Murrieta, California (May 2022) | HVS for City of Murrieta | 120000 USD/key (2022) | high | https://www.murrietaca.gov/DocumentCenter/View/7349/HVS-Feasibility-Study-2022---Proposed-Limited-Service-Hotel-PDF
hospitality/hotel-select-service.json#e8 | North America Quarterly Construction Cost Report, Q2 2026 | Rider Levett Bucknall | 406 USD/sf (2026) | medium | https://www.rlb.com/wp-content/uploads/sites/4/2026/06/Q2-2026-QCR_7.7.2026.pdf