## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · I-20 Logistics Center — bulk warehouse · Total $47,315,978
COST SUMMARY
Construction hard cost | 28675226.26
FF&E | 0
Design + construction contingency | 2638120.82
Hard cost subtotal | 31313347.08
Soft costs | 4138491.68
Impact & tap fees | 2106721.6
Developer fee | 1519540.72
Financing (interest + fees) | 1409519.3
Soft cost contingency | 429957.73
Soft cost subtotal | 9604231.03
Land & acquisition | 6398400
Total project cost | 47315978.11
BASIS
Location | Dallas-Fort Worth, TX (factor 0.840)
Gross building SF | 320,000
Site acres | 24.00
Cost per acre | 1971499.0879
Research data version | 2026.7c60a42879
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.7c60a42879), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · I-20 Logistics Center — bulk warehouse · Total $47,315,978
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Building A | Warehouse / distribution | 320000 SF | 31313347.08 | 9604231.03 | 6398400 | 47315978.11 | 147.8624 | 147.8624 | within ($80–$230)
Total |  |  | 31313347.08 | 9604231.03 | 6398400 | 47315978.11

## Phases
FINISHES SOLUTIONS
Cost by Phase · I-20 Logistics Center — bulk warehouse · Total $47,315,978
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 18 | 2027-12 | 5.9% | 31313347.08 | 9604231.03 | 6398400 | 47315978.11 | 28389586.87 | 1125623.43
Total |  |  |  |  | 31313347.08 | 9604231.03 | 6398400 | 47315978.11

## Detail
FINISHES SOLUTIONS
Line-Item Detail · I-20 Logistics Center — bulk warehouse · Total $47,315,978
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Building A | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 2855918.34
Building A | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 6283020.33
Building A | Phase 1 | Construction | 05 00 00 | Metals |  |  |  | 3141510.17
Building A | Phase 1 | Construction | 07 00 00 | Thermal & Moisture Protection |  |  |  | 1999142.83
Building A | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 1142367.33
Building A | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 571183.67
Building A | Phase 1 | Construction | 10 00 00 | Specialties |  |  |  | 285591.83
Building A | Phase 1 | Construction | 21 00 00 | Fire Suppression — balance |  |  |  | 8160.31
Building A | Phase 1 | Construction | 22 00 00 | Plumbing |  |  |  | 428387.75
Building A | Phase 1 | Construction | 23 00 00 | HVAC |  |  |  | 713979.59
Building A | Phase 1 | Construction | 26 00 00 | Electrical |  |  |  | 1570755.08
Building A | Phase 1 | Construction | 27 00 00 | Communications |  |  |  | 142795.92
Building A | Phase 1 | Construction | 28 00 00 | Electronic Safety & Security |  |  |  | 285591.83
Building A | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 2284734.66
Building A | Phase 1 | Construction | 32 00 00 | Exterior Improvements — balance |  |  |  | 3171905.41
Building A | Phase 1 | Construction | 33 00 00 | Utilities |  |  |  | 1713551
Building A | Phase 1 | Construction | 11 00 00 | Dock door package (9×10 insulated door, 30k-lb hydraulic leveler, seal, bumpers, dock light) (within baseline) | 42.56 | ea | 16014.5941 | 681581.12
Building A | Phase 1 | Construction | 21 00 00 | ESFR sprinkler system incl. fire pump allowance (within baseline) | 320000 | SF | 3.5588 | 1138815.58
Building A | Phase 1 | Construction | 32 00 00 | Trailer parking stalls (heavy-duty concrete, 12×55 ft) (within baseline) | 32 | space | 8007.297 | 256233.51
Building A | Phase 1 | Contingency | 99 02 00 | Design contingency | 4 | % of hard |  | 1147009.05
Building A | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 5 | % of hard |  | 1491111.77
Building A | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 6.79 | % of hard |  | 1947347.46
Building A | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 1.04 | % of hard |  | 299591.92
Building A | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 1.04 | % of hard |  | 299591.92
Building A | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.73 | % of hard |  | 209714.34
Building A | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.42 | % of hard |  | 119836.77
Building A | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.31 | % of hard |  | 89877.57
Building A | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.84 | % of hard |  | 239673.53
Building A | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.42 | % of hard |  | 119836.77
Building A | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.84 | % of hard |  | 239673.53
Building A | Phase 1 | Soft costs | SC | Owner's representative / project management | 1.57 | % of hard |  | 449387.87
Building A | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 21000 | 21000
Building A | Phase 1 | Impact & tap fees | SC | Total impact fees — industrial | 320 | 1,000 SF | 4225.85 | 1352272
Building A | Phase 1 | Impact & tap fees | SC | Water capacity / tap / impact fee | 80 | EDU | 4838.18 | 387054.4
Building A | Phase 1 | Impact & tap fees | SC | Sewer (wastewater) capacity / tap / impact fee | 80 | EDU | 4592.44 | 367395.2
Building A | Phase 1 | Contingency | SC | Soft cost contingency | 7 | % of soft |  | 429957.73
Building A | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 6240000
Building A | Phase 1 | Land | LAND | Land closing costs |  |  |  | 124800
Building A | Phase 1 | Land | LAND | Land due diligence |  |  |  | 33600
Building A | Phase 1 | Soft costs | SC | Real estate taxes during construction | 1.5 | years | 68640 | 102960
Building A | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 1519540.72
Building A | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 1125623.43
Building A | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 283895.87
TOTAL |  |  |  | Total project cost |  |  |  | 47315978.11

## Draws
FINISHES SOLUTIONS
Draw Schedules · I-20 Logistics Center — bulk warehouse · Total $47,315,978
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 4464538.56 | 6398400 | 11146834.43 | 0 | 0 | 0
2027-04 | 237860.05 | 207231.85 | 0 | 445091.9 | 0 | 0 | 0
2027-05 | 706352.88 | 207231.83 | 0 | 913584.71 | 0 | 0 | 0
2027-06 | 1153383.58 | 207231.83 | 0 | 1360615.41 | 0 | 0 | 0
2027-07 | 1565369.25 | 207231.83 | 0 | 1772601.08 | 0 | 0 | 0
2027-08 | 1929792.01 | 207231.88 | 0 | 2137023.89 | 0 | 0 | 0
2027-09 | 2235578.98 | 207231.83 | 0 | 1150639.82 | 1292170.99 | 0 | 1292170.99
2027-10 | 2473439.05 | 207231.87 | 0 | 0 | 2680670.92 | 7537.66 | 3980379.57
2027-11 | 2636144.88 | 207231.82 | 0 | 0 | 2843376.7 | 23218.88 | 6846975.15
2027-12 | 2718752.82 | 207231.86 | 0 | 0 | 2925984.68 | 39940.69 | 9812900.52
2028-01 | 2718752.85 | 207231.86 | 0 | 0 | 2925984.71 | 57241.92 | 12796127.15
2028-02 | 2636144.88 | 207231.86 | 0 | 0 | 2843376.74 | 74644.08 | 15714147.97
2028-03 | 2473439.04 | 207231.8 | 0 | 0 | 2680670.84 | 91665.86 | 18486484.67
2028-04 | 2235579.02 | 207231.85 | 0 | 0 | 2442810.87 | 107837.83 | 21037133.37
2028-05 | 1929792.01 | 207231.85 | 0 | 0 | 2137023.86 | 122716.61 | 23296873.84
2028-06 | 1565369.27 | 207231.85 | 0 | 0 | 1772601.12 | 135898.43 | 25205373.39
2028-07 | 1153383.57 | 207231.8 | 0 | 0 | 1360615.37 | 147031.34 | 26713020.1
2028-08 | 706352.9 | 207231.85 | 0 | 0 | 913584.75 | 155825.95 | 27782430.8
2028-09 | 237860.04 | 207231.85 | 0 | 0 | 445091.89 | 162064.18 | 28389586.87

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · I-20 Logistics Center — bulk warehouse · Total $47,315,978
ASSUMPTIONS
Building A — baseline price | $100 / SF · Researched (industrial/warehouse-distribution.json)
Building A — factors | regional 0.84 · quality 1 · size 1.0072 · escalation 1.0592
Building A — research note | Bulk tilt-wall or precast distribution (32–40' clear) is one of the cheapest building types per SF; cost is driven by building size (fixed costs spread over more SF), slab/structure spec, clear height, dock-door count and the size of the truck courts and trailer parking. Data quality is good: Cushman & Wakefield publishes an annual model-building guide (2026: $78–$144 psf by size) and RLB publishes metro ranges, but the two differ in scope and basis, so the default leans on C&W for big-box product and uses RLB for the spread.
Phase 1 — schedule | 2027-03, 18 months, midpoint 2027-12, escalation 5.92% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (49)
Ref | Source | Publisher | Value | Confidence | URL
_blocks/building-systems.json#e3 | How Much Does a Commercial Fire Sprinkler System Cost? | ThePricer | 1.5–3 USD/sf (2026) | low | https://www.thepricer.org/commercial-fire-sprinkler-system-cost/
_blocks/building-systems.json#e4 | How Much Does a Commercial Fire Sprinkler System Cost? | ThePricer | 4–9 USD/sf (2026) | low | https://www.thepricer.org/commercial-fire-sprinkler-system-cost/
_blocks/paving.json#e7 | Item Average Unit Cost, From 2025/09/01 to 2026/08/31, Statewide (historical-item-averages-statewide-12-months) | Florida Department of Transportation | 82 USD/sy (2026) | medium | https://fdotwww.blob.core.windows.net/sitefinity/docs/default-source/fpo/fpc/reports/historicalitemaveragecost/moving/statewide/pdf/historical-item-averages-statewide-12-months.pdf?sfvrsn=32501f5b_15
_blocks/paving.json#e8 | Weighted Average Unit Prices from 6/25/2025 to 6/24/2026 | Arkansas Department of Transportation, Program Management Division | 67.98 USD/sy (2025) | high | https://media.ark.org/ardot/June-24-2026-Weighted-Averages-Prices.pdf
_common/fees.json#e1 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 13627 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e2 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 6460 USD/unit (2019) | medium | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e6 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 3942 USD/1000sf (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
industrial/warehouse-distribution.json#e1 | 2026 Americas Industrial Construction Cost Guide (landing page) | Cushman & Wakefield | 87 USD/sf (2026) | high | https://www.cushmanwakefield.com/en/united-states/insights/industrial-construction-cost-guide
industrial/warehouse-distribution.json#e10 | Quarterly Construction Cost Report 2026 Third Quarter (North America) | Rider Levett Bucknall | 155–245 USD/sf (2026) | high | https://www.rlb.com/wp-content/uploads/sites/4/2026/09/Q3-2026-QCR.pdf
industrial/warehouse-distribution.json#e11 | Quarterly Construction Cost Report 2026 Third Quarter (North America) | Rider Levett Bucknall | 150–230 USD/sf (2026) | high | https://www.rlb.com/wp-content/uploads/sites/4/2026/09/Q3-2026-QCR.pdf
industrial/warehouse-distribution.json#e12 | Warehouse Construction Cost Model (Brick Veneer / Reinforced Concrete) | Gordian RSMeans | 119.27 USD/sf (2019) | medium | https://www.rsmeans.com/model-pages/warehouse
industrial/warehouse-distribution.json#e13 | Tilt-Up Concrete Construction Cost Per Square Foot (2026) | Terrapin Construction Group | 115–185 USD/sf (2026) | low | https://terrapincg.com/news/tilt-up-concrete-construction-cost-per-square-foot-2026
industrial/warehouse-distribution.json#e2 | 2026 Americas Industrial Construction Cost Guide (landing page) | Cushman & Wakefield | 78 USD/sf (2026) | high | https://www.cushmanwakefield.com/en/united-states/insights/industrial-construction-cost-guide
industrial/warehouse-distribution.json#e3 | 2026 Americas Industrial Construction Cost Guide (landing page) | Cushman & Wakefield | 144 USD/sf (2026) | high | https://www.cushmanwakefield.com/en/united-states/insights/industrial-construction-cost-guide
industrial/warehouse-distribution.json#e5 | Industrial Construction Costs Rise Across Americas | CRE Daily | 0.34–0.37 pct (2026) | medium | https://www.credaily.com/?p=223266
industrial/warehouse-distribution.json#e7 | Quarterly Construction Cost Report 2026 Third Quarter (North America) | Rider Levett Bucknall | 140–228 USD/sf (2026) | medium | https://www.rlb.com/wp-content/uploads/sites/4/2026/09/Q3-2026-QCR.pdf
industrial/warehouse-distribution.json#e8 | Quarterly Construction Cost Report 2026 Third Quarter (North America) | Rider Levett Bucknall | 75–155 USD/sf (2026) | high | https://www.rlb.com/wp-content/uploads/sites/4/2026/09/Q3-2026-QCR.pdf
industrial/warehouse-distribution.json#e9 | Quarterly Construction Cost Report 2026 Third Quarter (North America) | Rider Levett Bucknall | 85–170 USD/sf (2026) | high | https://www.rlb.com/wp-content/uploads/sites/4/2026/09/Q3-2026-QCR.pdf