## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Desert Ridge MOB · Total $33,869,764
COST SUMMARY
Construction hard cost | 19581080.86
FF&E | 1732182.74
Design + construction contingency | 2731712.02
Hard cost subtotal | 24044975.62
Soft costs | 4335069.39
Impact & tap fees | 358557.98
Developer fee | 1158836.04
Financing (interest + fees) | 1048427.3
Soft cost contingency | 232298.04
Soft cost subtotal | 7133188.75
Land & acquisition | 2691600
Total project cost | 33869764.37
BASIS
Location | Phoenix, AZ (factor 0.990)
Gross building SF | 45,000
Site acres | 4.09
Cost per acre | 8279275.7349
Research data version | 2026.7c60a42879
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.7c60a42879), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Desert Ridge MOB · Total $33,869,764
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Medical office building | Medical office building | 45000 SF | 24044975.62 | 7133188.75 | 2691600 | 33869764.37 | 752.6614 | 752.6614 | within ($261–$1,202)
Total |  |  | 24044975.62 | 7133188.75 | 2691600 | 33869764.37

## Phases
FINISHES SOLUTIONS
Cost by Phase · Desert Ridge MOB · Total $33,869,764
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 20 | 2028-01 | 6.3% | 24044975.62 | 7133188.75 | 2691600 | 33869764.37 | 20321858.62 | 845208.71
Total |  |  |  |  | 24044975.62 | 7133188.75 | 2691600 | 33869764.37

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Desert Ridge MOB · Total $33,869,764
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Medical office building | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 1709475.93
Medical office building | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 1329592.39
Medical office building | Phase 1 | Construction | 04 00 00 | Masonry |  |  |  | 379883.54
Medical office building | Phase 1 | Construction | 05 00 00 | Metals |  |  |  | 1329592.39
Medical office building | Phase 1 | Construction | 06 00 00 | Wood, Plastics & Composites |  |  |  | 759767.08
Medical office building | Phase 1 | Construction | 07 00 00 | Thermal & Moisture Protection |  |  |  | 1139650.62
Medical office building | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 1329592.39
Medical office building | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 2279301.23
Medical office building | Phase 1 | Construction | 10 00 00 | Specialties |  |  |  | 379883.54
Medical office building | Phase 1 | Construction | 21 00 00 | Fire Suppression |  |  |  | 379883.54
Medical office building | Phase 1 | Construction | 22 00 00 | Plumbing |  |  |  | 1329592.39
Medical office building | Phase 1 | Construction | 23 00 00 | HVAC |  |  |  | 2279301.24
Medical office building | Phase 1 | Construction | 26 00 00 | Electrical |  |  |  | 1899417.69
Medical office building | Phase 1 | Construction | 27 00 00 | Communications |  |  |  | 379883.54
Medical office building | Phase 1 | Construction | 28 00 00 | Electronic Safety & Security |  |  |  | 189941.77
Medical office building | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 379883.54
Medical office building | Phase 1 | Construction | 33 00 00 | Utilities |  |  |  | 379883.54
Medical office building | Phase 1 | Construction | 32 00 00 | On-site work incl. surface parking (carve-out) (within baseline) | 45000 | SF | 32.991 | 1484592.8
Medical office building | Phase 1 | Construction | 14 00 00 | Hydraulic passenger/stretcher elevator (within baseline) | 2 | ea | 120980.8478 | 241961.7
Medical office building | Phase 1 | FF&E | 12 00 00 | Furniture, fixtures & equipment | 45000 | SF | 38.4929 | 1732182.74
Medical office building | Phase 1 | Contingency | 99 02 00 | Design contingency | 7 | % of hard |  | 1370675.66
Medical office building | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 6 | % of hard |  | 1361036.36
Medical office building | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 9.7 | % of hard |  | 2067704.68
Medical office building | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 1.49 | % of hard |  | 318108.41
Medical office building | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 1.49 | % of hard |  | 318108.41
Medical office building | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 1.04 | % of hard |  | 222675.89
Medical office building | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.6 | % of hard |  | 127243.37
Medical office building | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.45 | % of hard |  | 95432.52
Medical office building | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 1.19 | % of hard |  | 254486.73
Medical office building | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.6 | % of hard |  | 127243.36
Medical office building | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 1.19 | % of hard |  | 254486.73
Medical office building | Phase 1 | Soft costs | SC | Owner's representative / project management | 2.24 | % of hard |  | 477162.62
Medical office building | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 24750 | 24750
Medical office building | Phase 1 | Impact & tap fees | SC | Total impact fees — office | 45 | 1,000 SF | 5610.3 | 252463.5
Medical office building | Phase 1 | Impact & tap fees | SC | Water capacity / tap / impact fee | 11.25 | EDU | 4838.18 | 54429.53
Medical office building | Phase 1 | Impact & tap fees | SC | Sewer (wastewater) capacity / tap / impact fee | 11.25 | EDU | 4592.44 | 51664.95
Medical office building | Phase 1 | Contingency | SC | Soft cost contingency | 5 | % of soft |  | 232298.04
Medical office building | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 2600000
Medical office building | Phase 1 | Land | LAND | Land closing costs |  |  |  | 52000
Medical office building | Phase 1 | Land | LAND | Land due diligence |  |  |  | 39600
Medical office building | Phase 1 | Soft costs | SC | Real estate taxes during construction | 1.67 | years | 28600 | 47666.67
Medical office building | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 1158836.04
Medical office building | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 845208.71
Medical office building | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 203218.59
TOTAL |  |  |  | Total project cost |  |  |  | 33869764.37

## Draws
FINISHES SOLUTIONS
Draw Schedules · Desert Ridge MOB · Total $33,869,764
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 2864553.6 | 2691600 | 5759372.19 | 0 | 0 | 0
2027-04 | 148016.77 | 161010.39 | 0 | 309027.16 | 0 | 0 | 0
2027-05 | 440405.65 | 161010.39 | 0 | 601416.04 | 0 | 0 | 0
2027-06 | 721950.29 | 161010.39 | 0 | 882960.68 | 0 | 0 | 0
2027-07 | 985718.15 | 161010.4 | 0 | 1146728.55 | 0 | 0 | 0
2027-08 | 1225214.31 | 161010.39 | 0 | 1386224.7 | 0 | 0 | 0
2027-09 | 1434541.62 | 161010.39 | 0 | 1595552.01 | 0 | 0 | 0
2027-10 | 1608545.76 | 161010.37 | 0 | 1769556.13 | 0 | 0 | 0
2027-11 | 1742942.17 | 161010.44 | 0 | 97068.29 | 1806884.32 | 0 | 1806884.32
2027-12 | 1834421.63 | 161010.36 | 0 | 0 | 1995431.99 | 10540.16 | 3812856.47
2028-01 | 1880731.48 | 161010.36 | 0 | 0 | 2041741.84 | 22241.66 | 5876839.97
2028-02 | 1880731.5 | 161010.44 | 0 | 0 | 2041741.94 | 34281.57 | 7952863.48
2028-03 | 1834421.59 | 161010.36 | 0 | 0 | 1995431.95 | 46391.7 | 9994687.13
2028-04 | 1742942.17 | 161010.43 | 0 | 0 | 1903952.6 | 58302.34 | 11956942.07
2028-05 | 1608545.74 | 161010.36 | 0 | 0 | 1769556.1 | 69748.83 | 13796247
2028-06 | 1434541.62 | 161010.43 | 0 | 0 | 1595552.05 | 80478.11 | 15472277.16
2028-07 | 1225214.31 | 161010.41 | 0 | 0 | 1386224.72 | 90254.95 | 16948756.83
2028-08 | 985718.15 | 161010.36 | 0 | 0 | 1146728.51 | 98867.75 | 18194353.09
2028-09 | 721950.29 | 161010.41 | 0 | 0 | 882960.7 | 106133.73 | 19183447.52
2028-10 | 440405.65 | 161010.36 | 0 | 0 | 601416.01 | 111903.44 | 19896766.97
2028-11 | 148016.77 | 161010.41 | 0 | 0 | 309027.18 | 116064.47 | 20321858.62

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Desert Ridge MOB · Total $33,869,764
ASSUMPTIONS
Medical office building — baseline price | $418 / SF · Researched (commercial/medical-office.json)
Medical office building — factors | regional 0.99 · quality 1 · size 0.9906 · escalation 1.0626
Medical office building — research note | Outpatient medical office (physician suites, exam rooms, light procedure and imaging) delivered complete: shell plus typical medical build-out with heavier HVAC, plumbing at every exam room and higher electrical density. Public data disagree widely — RSMeans national project data (~$250/SF in 2022) vs. Cumming 2025 metro ranges ($400–1,050) — so the mid is a reasoned blend; verify against a local estimate.
Phase 1 — schedule | 2027-03, 20 months, midpoint 2028-01, escalation 6.26% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (40)
Ref | Source | Publisher | Value | Confidence | URL
_blocks/building-systems.json#e1 | How Much Does Elevator Installation Cost? | ThePricer | 75000–350000 USD/ea (2026) | low | https://www.thepricer.org/elevator-installation-costs/
_common/fees.json#e1 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 13627 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e2 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 6460 USD/unit (2019) | medium | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e5 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 5408 USD/1000sf (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
commercial/medical-office.json#e1 | Market Analysis Q4 2025 — Typical Construction Cost Range (Cost Per Unit 2025) | Cumming Group | 450–690 USD/sf (2025) | high | https://cumming-group.com/wp-content/uploads/2025/12/CummingGroup_Q4_2025_MarketingAnalysis_2.13.26.pdf
commercial/medical-office.json#e2 | 2022 Project Costs — 50 17 00 Project Costs per S.F. | Gordian / RSMeans | 250 USD/sf (2022) | high | https://www.rsmeans.com/media/wysiwyg/quarterly_updates/2022-Project-Costs-per-Square-Foot.pdf
commercial/medical-office.json#e3 | Construction Cost Estimates for a Medical Office, 1 Story in National, US (2019 RSMeans data) | Gordian / RSMeans | 217.02 USD/sf (2019) | medium | https://www.rsmeans.com/model-pages/medical-office-1-story.aspx
commercial/medical-office.json#e4 | Construction Cost Estimates for a Medical Office, 1 Story in National, US (2019 RSMeans data) | Gordian / RSMeans | 0.09 pct | medium | https://www.rsmeans.com/model-pages/medical-office-1-story.aspx
commercial/medical-office.json#e5 | Construction Cost Trends / 2025 — Houston | Kirksey Architecture | 14–20 USD/sf (2025) | medium | https://www.kirksey.com/CMSPages/GetFile.aspx?guid=1c8a21ff-de0e-4629-b9b0-7f38f62c502b