## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Outparcel QSR with drive-thru · Total $4,048,466
COST SUMMARY
Construction hard cost | 1488070.39
FF&E | 597153.72
Design + construction contingency | 247173.73
Hard cost subtotal | 2332397.84
Soft costs | 280910.22
Impact & tap fees | 26258.17
Developer fee | 106538.6
Financing (interest + fees) | 69862.25
Soft cost contingency | 23898.8
Soft cost subtotal | 507468.04
Land & acquisition | 1208600
Total project cost | 4048465.88
BASIS
Location | Atlanta, GA (factor 0.890)
Gross building SF | 2,800
Site acres | 0.90
Cost per acre | 4482230.0814
Research data version | 2026.7c60a42879
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.7c60a42879), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Outparcel QSR with drive-thru · Total $4,048,466
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
QSR building | Retail pad / QSR | 2800 SF | 2332397.84 | 507468.04 | 1208600 | 4048465.88 | 1445.8807 | 1445.8807 | within ($397–$1,359)
Total |  |  | 2332397.84 | 507468.04 | 1208600 | 4048465.88

## Phases
FINISHES SOLUTIONS
Cost by Phase · Outparcel QSR with drive-thru · Total $4,048,466
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 8 | 2027-07 | 4.2% | 2332397.84 | 507468.04 | 1208600 | 4048465.88 | 2429079.53 | 45571.45
Total |  |  |  |  | 2332397.84 | 507468.04 | 1208600 | 4048465.88

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Outparcel QSR with drive-thru · Total $4,048,466
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
QSR building | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 97014.31
QSR building | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 72760.73
QSR building | Phase 1 | Construction | 04 00 00 | Masonry |  |  |  | 48507.16
QSR building | Phase 1 | Construction | 05 00 00 | Metals |  |  |  | 36380.37
QSR building | Phase 1 | Construction | 06 00 00 | Wood, Plastics & Composites |  |  |  | 48507.16
QSR building | Phase 1 | Construction | 07 00 00 | Thermal & Moisture Protection |  |  |  | 48507.16
QSR building | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 48507.16
QSR building | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 84887.52
QSR building | Phase 1 | Construction | 10 00 00 | Specialties |  |  |  | 12126.79
QSR building | Phase 1 | Construction | 11 00 00 | Equipment |  |  |  | 12126.79
QSR building | Phase 1 | Construction | 21 00 00 | Fire Suppression |  |  |  | 12126.79
QSR building | Phase 1 | Construction | 22 00 00 | Plumbing |  |  |  | 60633.94
QSR building | Phase 1 | Construction | 23 00 00 | HVAC — balance |  |  |  | 45387.4
QSR building | Phase 1 | Construction | 26 00 00 | Electrical |  |  |  | 84887.52
QSR building | Phase 1 | Construction | 27 00 00 | Communications |  |  |  | 12126.79
QSR building | Phase 1 | Construction | 28 00 00 | Electronic Safety & Security |  |  |  | 12126.79
QSR building | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 97014.31
QSR building | Phase 1 | Construction | 33 00 00 | Utilities |  |  |  | 121267.89
QSR building | Phase 1 | Construction | 32 00 00 | On-site improvements (grading, paving incl. drive-thru lane, utilities, landscaping) (within baseline) | 1 | LS | 484703.473 | 484703.47
QSR building | Phase 1 | Construction | 23 00 00 | Kitchen exhaust hood, make-up air and fire suppression (within baseline) | 1 | LS | 48470.3445 | 48470.34
QSR building | Phase 1 | FF&E | 12 00 00 | Furniture, fixtures & equipment | 2800 | SF | 213.2692 | 597153.72
QSR building | Phase 1 | Contingency | 99 02 00 | Design contingency | 5 | % of hard |  | 74403.52
QSR building | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 8 | % of hard |  | 172770.21
QSR building | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 5.82 | % of hard |  | 121378.72
QSR building | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 0.9 | % of hard |  | 18673.65
QSR building | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 0.9 | % of hard |  | 18673.65
QSR building | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.63 | % of hard |  | 13071.55
QSR building | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.36 | % of hard |  | 7469.46
QSR building | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.27 | % of hard |  | 5602.09
QSR building | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.72 | % of hard |  | 14938.92
QSR building | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.36 | % of hard |  | 7469.46
QSR building | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.72 | % of hard |  | 14938.92
QSR building | Phase 1 | Soft costs | SC | Owner's representative / project management | 1.34 | % of hard |  | 28010.47
QSR building | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 22250 | 22250
QSR building | Phase 1 | Impact & tap fees | SC | Total impact fees — retail | 2.8 | 1,000 SF | 7020.26 | 19656.73
QSR building | Phase 1 | Impact & tap fees | SC | Water capacity / tap / impact fee | 0.7 | EDU | 4838.18 | 3386.73
QSR building | Phase 1 | Impact & tap fees | SC | Sewer (wastewater) capacity / tap / impact fee | 0.7 | EDU | 4592.44 | 3214.71
QSR building | Phase 1 | Contingency | SC | Soft cost contingency | 8 | % of soft |  | 23898.8
QSR building | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 1150000
QSR building | Phase 1 | Land | LAND | Land closing costs |  |  |  | 23000
QSR building | Phase 1 | Land | LAND | Land due diligence |  |  |  | 35600
QSR building | Phase 1 | Soft costs | SC | Real estate taxes during construction | 0.67 | years | 12650 | 8433.33
QSR building | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 106538.6
QSR building | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 45571.45
QSR building | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 24290.8
TOTAL |  |  |  | Total project cost |  |  |  | 4048465.88

## Draws
FINISHES SOLUTIONS
Draw Schedules · Outparcel QSR with drive-thru · Total $4,048,466
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 194162.63 | 1208600 | 1427053.43 | 0 | 0 | 0
2027-04 | 88771.59 | 30430.44 | 0 | 119202.03 | 0 | 0 | 0
2027-05 | 252800.19 | 30430.42 | 0 | 73130.89 | 210099.72 | 0 | 210099.72
2027-06 | 378342.13 | 30430.41 | 0 | 0 | 408772.54 | 1225.58 | 620097.84
2027-07 | 446285.01 | 30430.41 | 0 | 0 | 476715.42 | 3617.24 | 1100430.5
2027-08 | 446284.96 | 30430.38 | 0 | 0 | 476715.34 | 6419.18 | 1583565.02
2027-09 | 378342.19 | 30430.37 | 0 | 0 | 408772.56 | 9237.46 | 2001575.04
2027-10 | 252800.19 | 30430.37 | 0 | 0 | 283230.56 | 11675.85 | 2296481.45
2027-11 | 88771.58 | 30430.36 | 0 | 0 | 119201.94 | 13396.14 | 2429079.53

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Outparcel QSR with drive-thru · Total $4,048,466
ASSUMPTIONS
QSR building — baseline price | $601 / SF · Researched (commercial/retail-pad-qsr.json)
QSR building — factors | regional 0.89 · quality 1 · size 0.991 · escalation 1.042
QSR building — research note | Ground-up freestanding quick-service restaurant (1,400–3,500 SF) with drive-thru on a 0.6–1.5 acre outparcel. Cost per SF is high because a small building carries a full commercial kitchen MEP load plus a large share of site work (drive-thru stacking lane, parking, utilities), which franchisor data puts at roughly one-third of building+site cost. Data quality is good: seven 2026 franchise disclosure documents (Item 7) publish building and site-work ranges drawn from recent company and franchisee projects; per-SF conversion depends on assumed building size.
Phase 1 — schedule | 2027-03, 8 months, midpoint 2027-07, escalation 4.20% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (49)
Ref | Source | Publisher | Value | Confidence | URL
_common/fees.json#e1 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 13627 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e2 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 6460 USD/unit (2019) | medium | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e4 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 6760 USD/1000sf (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
commercial/retail-pad-qsr.json#e1 | Franchise Disclosure Document, Quality Is Our Recipe, LLC (Wendy's), FDD-2026, Item 7 | Quality Is Our Recipe, LLC (hosted by Restaurant Finance Monitor) | 1033292–2200000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/Wendys-2025.pdf
commercial/retail-pad-qsr.json#e10 | Average Cost to Build a QSR in the USA (2026 Complete Guide) | Terrapin Construction Group | 535–555 USD/sf (2025) | low | https://terrapincg.com/news/average-cost-to-build-a-qsr-usa
commercial/retail-pad-qsr.json#e11 | McDonald's USA Franchise Disclosure Document (2026), Item 7 | McDonald's USA, LLC (hosted by Restaurant Finance Monitor) | 1100000–1850000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/McDonalds-2025.pdf
commercial/retail-pad-qsr.json#e12 | Franchise Disclosure Document, Quality Is Our Recipe, LLC (Wendy's), FDD-2026, Item 7 | Quality Is Our Recipe, LLC (hosted by Restaurant Finance Monitor) | 380165–650000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/Wendys-2025.pdf
commercial/retail-pad-qsr.json#e14 | Zaxbys Franchise Disclosure Document (04/26 FDD), Item 7 | Zaxby's SPE Franchisor LLC (hosted by Restaurant Finance Monitor) | 47000–260000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/Zaxbys-2025.pdf
commercial/retail-pad-qsr.json#e15 | Jack in the Box Franchise Disclosure Document (FDD 03/26), Item 7 | Different Rules, LLC (Jack in the Box) (hosted by Restaurant Finance Monitor) | 46500–250000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/Jack-In-The-Box-2025.pdf
commercial/retail-pad-qsr.json#e16 | A&W Restaurants Franchise Disclosure Document (A&W FDD- 4/2026), Item 7 | A&W Restaurants, Inc. (hosted by Restaurant Finance Monitor) | 30000–84000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/A-And-W-2025.pdf
commercial/retail-pad-qsr.json#e2 | Taco Bell Franchise Disclosure Document (Traditional FDD 2026), Item 7 | Taco Bell Franchisor, LLC (hosted by Restaurant Finance Monitor) | 1000000–2000000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/Taco-Bell-2025.pdf
commercial/retail-pad-qsr.json#e3 | Popeyes Louisiana Kitchen Franchise Disclosure Document (03/2026), Item 7 | Popeyes Louisiana Kitchen, Inc. (hosted by Restaurant Finance Monitor) | 740000–2400000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/Popeyes-2025.pdf
commercial/retail-pad-qsr.json#e4 | Zaxbys Franchise Disclosure Document (04/26 FDD), Item 7 | Zaxby's SPE Franchisor LLC (hosted by Restaurant Finance Monitor) | 790000–2290000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/Zaxbys-2025.pdf
commercial/retail-pad-qsr.json#e5 | Jack in the Box Franchise Disclosure Document (FDD 03/26), Item 7 | Different Rules, LLC (Jack in the Box) (hosted by Restaurant Finance Monitor) | 963000–2075400 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/Jack-In-The-Box-2025.pdf
commercial/retail-pad-qsr.json#e6 | Sonic Franchise Disclosure Document (2026 FDD, issued March 26, 2026), Item 7 | Sonic Franchising LLC (hosted by Restaurant Finance Monitor) | 1050000–1500000 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/Sonic-2025.pdf
commercial/retail-pad-qsr.json#e7 | A&W Restaurants Franchise Disclosure Document (A&W FDD- 4/2026), Item 7 | A&W Restaurants, Inc. (hosted by Restaurant Finance Monitor) | 500000–869484 USD/site (2025) | high | https://www.restfinance.com/app/pdf/fdd/A-And-W-2025.pdf
commercial/retail-pad-qsr.json#e8 | Construction Cost Estimates for Fast Food Restaurant in National, US (model page) | Gordian / RSMeans | 208.3 USD/sf (2019) | medium | https://www.rsmeans.com/model-pages/fast-food-restaurant
commercial/retail-pad-qsr.json#e9 | TABS project TABS2025010278 — McDonald's Fulshear (42-3567) | Texas Department of Licensing and Regulation | 205 USD/sf (2025) | low | https://www.tdlr.texas.gov/TABS/Projects/TABS2025010278