## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Fulton Market office TI · Total $8,621,399
COST SUMMARY
Construction hard cost | 4731691.21
FF&E | 1779614.43
Design + construction contingency | 776415.78
Hard cost subtotal | 7287721.42
Soft costs | 811606.68
Impact & tap fees | 0
Developer fee | 325596.34
Financing (interest + fees) | 155894.71
Soft cost contingency | 40580.33
Soft cost subtotal | 1333678.06
Land & acquisition | 0
Total project cost | 8621399.48
BASIS
Location | Chicago, IL (factor 1.210)
Gross building SF | 22,000
Site acres | —
Cost per acre
Research data version | 2026.7c60a42879
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.7c60a42879), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Fulton Market office TI · Total $8,621,399
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Tenant improvement — floors 6–7 | Office tenant improvement | 22000 SF | 7287721.42 | 1333678.06 | 0 | 8621399.48 | 391.8818 | 391.8818 | within ($90–$450)
Total |  |  | 7287721.42 | 1333678.06 | 0 | 8621399.48

## Phases
FINISHES SOLUTIONS
Cost by Phase · Fulton Market office TI · Total $8,621,399
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 11 | 2027-09 | 4.9% | 7287721.42 | 1333678.06 | 0 | 8621399.48 | 5172839.69 | 104166.31
Total |  |  |  |  | 7287721.42 | 1333678.06 | 0 | 8621399.48

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Fulton Market office TI · Total $8,621,399
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Tenant improvement — floors 6–7 | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 442715.88
Tenant improvement — floors 6–7 | Phase 1 | Construction | 06 00 00 | Wood, Plastics & Composites |  |  |  | 268066.5
Tenant improvement — floors 6–7 | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 434592.66
Tenant improvement — floors 6–7 | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 808261.11
Tenant improvement — floors 6–7 | Phase 1 | Construction | 10 00 00 | Specialties |  |  |  | 150279.7
Tenant improvement — floors 6–7 | Phase 1 | Construction | 21 00 00 | Fire Suppression |  |  |  | 101540.34
Tenant improvement — floors 6–7 | Phase 1 | Construction | 22 00 00 | Plumbing |  |  |  | 162464.55
Tenant improvement — floors 6–7 | Phase 1 | Construction | 23 00 00 | HVAC |  |  |  | 755460.13
Tenant improvement — floors 6–7 | Phase 1 | Construction | 26 00 00 | Electrical |  |  |  | 771706.59
Tenant improvement — floors 6–7 | Phase 1 | Construction | 27 00 00 | Communications |  |  |  | 105601.95
Tenant improvement — floors 6–7 | Phase 1 | Construction | 28 00 00 | Electronic Safety & Security |  |  |  | 60924.2
Tenant improvement — floors 6–7 | Phase 1 | Specialty & site | 27 00 00 | Low-voltage cabling, AV and security | 22000 | SF | 30.4581 | 670077.6
Tenant improvement — floors 6–7 | Phase 1 | FF&E | 12 00 00 | Furniture, fixtures & equipment | 22000 | SF | 80.8916 | 1779614.43
Tenant improvement — floors 6–7 | Phase 1 | Contingency | 99 02 00 | Design contingency | 5 | % of hard |  | 236584.56
Tenant improvement — floors 6–7 | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 8 | % of hard |  | 539831.22
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 5.82 | % of hard |  | 379016.3
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 0.9 | % of hard |  | 58310.2
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 0.9 | % of hard |  | 58310.2
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.63 | % of hard |  | 40817.14
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.36 | % of hard |  | 23324.08
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.27 | % of hard |  | 17493.06
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.72 | % of hard |  | 46648.16
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.36 | % of hard |  | 23324.08
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.72 | % of hard |  | 46648.16
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Owner's representative / project management | 1.34 | % of hard |  | 87465.3
Tenant improvement — floors 6–7 | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 30250 | 30250
Tenant improvement — floors 6–7 | Phase 1 | Contingency | SC | Soft cost contingency | 5 | % of soft |  | 40580.33
Tenant improvement — floors 6–7 | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 325596.34
Tenant improvement — floors 6–7 | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 104166.31
Tenant improvement — floors 6–7 | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 51728.4
TOTAL |  |  |  | Total project cost |  |  |  | 8621399.48

## Draws
FINISHES SOLUTIONS
Draw Schedules · Fulton Market office TI · Total $8,621,399
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 485069.56 | 0 | 536797.96 | 0 | 0 | 0
2027-04 | 147601.97 | 62973.98 | 0 | 210575.95 | 0 | 0 | 0
2027-05 | 430848.06 | 62973.97 | 0 | 493822.03 | 0 | 0 | 0
2027-06 | 679189.39 | 62973.97 | 0 | 742163.36 | 0 | 0 | 0
2027-07 | 872506.87 | 62974.03 | 0 | 935480.9 | 0 | 0 | 0
2027-08 | 995138.96 | 62973.96 | 0 | 529719.59 | 528393.33 | 0 | 528393.33
2027-09 | 1037150.89 | 62973.95 | 0 | 0 | 1100124.84 | 3082.29 | 1631600.46
2027-10 | 995138.98 | 62974.01 | 0 | 0 | 1058112.99 | 9517.67 | 2699231.12
2027-11 | 872506.86 | 62973.99 | 0 | 0 | 935480.85 | 15745.51 | 3650457.48
2027-12 | 679189.41 | 62973.99 | 0 | 0 | 742163.4 | 21294.34 | 4413915.22
2028-01 | 430848.06 | 62973.95 | 0 | 0 | 493822.01 | 25747.84 | 4933485.07
2028-02 | 147601.97 | 62973.99 | 0 | 0 | 210575.96 | 28778.66 | 5172839.69

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Fulton Market office TI · Total $8,621,399
ASSUMPTIONS
Tenant improvement — floors 6–7 — baseline price | $150 / SF · Researched (commercial/office-ti.json)
Tenant improvement — floors 6–7 — factors | regional 1.21 · quality 1 · size 0.9698 · escalation 1.0488
Tenant improvement — floors 6–7 — research note | Interior build-out of office space in an existing shell: partitions, ceilings, finishes, doors, millwork, distribution MEP and fire protection. Cost swings with density of enclosed offices, glass, millwork and MEP intensity; data quality is good (Cushman 42-city guide, Kirksey Texas surveys, Cumming metros, JLL).
Phase 1 — schedule | 2027-03, 11 months, midpoint 2027-09, escalation 4.88% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (34)
Ref | Source | Publisher | Value | Confidence | URL
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
commercial/office-ti.json#e1 | Construction Cost Trends / 2025 — Houston | Kirksey Architecture | 107–140 USD/sf (2025) | high | https://www.kirksey.com/CMSPages/GetFile.aspx?guid=1c8a21ff-de0e-4629-b9b0-7f38f62c502b
commercial/office-ti.json#e10 | U.S. & Canada Office Fit-Out Cost Guide (Q1 2026 pricing) | JLL | 0.1–0.12 pct | medium | https://www.jll.com/en-ca/guides/us-canada-office-fit-out-cost-guide-2025
commercial/office-ti.json#e2 | Construction Cost Trends / 2025 — Dallas | Kirksey Architecture | 108–133 USD/sf (2025) | high | https://www.kirksey.com/CMSPages/GetFile.aspx?guid=c5a9a83b-478c-495a-a4b2-cbb2a99377dc
commercial/office-ti.json#e3 | Construction Cost Trends / 2025 — Austin | Kirksey Architecture | 114–148 USD/sf (2025) | high | https://www.kirksey.com/CMSPages/GetFile.aspx?guid=7cfddae4-aa86-4325-b4d1-2084432c2273
commercial/office-ti.json#e4 | U.S. Office Fit Out Cost Guide (2026) | Cushman & Wakefield | 108.03–219.32 USD/sf (2026) | high | https://www.cushmanwakefield.com/en/united-states/insights/office-fit-out-cost-guide
commercial/office-ti.json#e5 | U.S. Office Fit Out Cost Guide (2026) | Cushman & Wakefield | 330.92 USD/sf (2026) | high | https://www.cushmanwakefield.com/en/united-states/insights/office-fit-out-cost-guide
commercial/office-ti.json#e6 | U.S. Office Fit Out Cost Guide (2026) | Cushman & Wakefield | text (2026) | high | https://www.cushmanwakefield.com/en/united-states/insights/office-fit-out-cost-guide
commercial/office-ti.json#e8 | Market Analysis Q4 2025 — Typical Construction Cost Range (Cost Per Unit 2025) | Cumming Group | 160–340 USD/sf (2025) | high | https://cumming-group.com/wp-content/uploads/2025/12/CummingGroup_Q4_2025_MarketingAnalysis_2.13.26.pdf
commercial/office-ti.json#e9 | Construction Cost Trends / 2025 — Dallas | Kirksey Architecture | 30–85 USD/sf (2025) | high | https://www.kirksey.com/CMSPages/GetFile.aspx?guid=c5a9a83b-478c-495a-a4b2-cbb2a99377dc