## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Cedar Pines tiny home community · Total $3,385,834
COST SUMMARY
Construction hard cost | 1612212.19
FF&E | 18724.15
Design + construction contingency | 340436.98
Hard cost subtotal | 1971373.32
Soft costs | 284933.14
Impact & tap fees | 541306.88
Developer fee | 113550.05
Financing (interest + fees) | 77732.67
Soft cost contingency | 41137.83
Soft cost subtotal | 1058660.57
Land & acquisition | 355800
Total project cost | 3385833.89
BASIS
Location | Austin, TX (factor 0.820)
Gross building SF | —
Site acres | 3.33
Cost per acre | 1015750.167
Research data version | 2026.7c60a42879
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.7c60a42879), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Cedar Pines tiny home community · Total $3,385,834
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Tiny home pads | Tiny home community | 40 pads | 1971373.32 | 1058660.57 | 355800 | 3385833.89 | 84645.8473 |  | within ($21,771–$141,514)
Total |  |  | 1971373.32 | 1058660.57 | 355800 | 3385833.89

## Phases
FINISHES SOLUTIONS
Cost by Phase · Cedar Pines tiny home community · Total $3,385,834
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 12 | 2027-09 | 4.9% | 1971373.32 | 1058660.57 | 355800 | 3385833.89 | 2031500.33 | 57417.67
Total |  |  |  |  | 1971373.32 | 1058660.57 | 355800 | 3385833.89

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Cedar Pines tiny home community · Total $3,385,834
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Tiny home pads | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 59863.92
Tiny home pads | Phase 1 | Construction | 07 00 00 | Thermal & Moisture Protection |  |  |  | 22448.97
Tiny home pads | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 11224.48
Tiny home pads | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 14965.98
Tiny home pads | Phase 1 | Construction | 10 00 00 | Specialties |  |  |  | 7482.99
Tiny home pads | Phase 1 | Construction | 22 00 00 | Plumbing |  |  |  | 29931.96
Tiny home pads | Phase 1 | Construction | 23 00 00 | HVAC |  |  |  | 11224.48
Tiny home pads | Phase 1 | Construction | 26 00 00 | Electrical |  |  |  | 104761.86
Tiny home pads | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 67346.91
Tiny home pads | Phase 1 | Construction | 32 00 00 | Exterior Improvements — balance |  |  |  | 127640.21
Tiny home pads | Phase 1 | Construction | 33 00 00 | Per-pad utility connection (water, sewer lateral, 50-100A electric pedestal/meter) (within baseline) | 40 | ea | 8425.9347 | 337037.39
Tiny home pads | Phase 1 | Construction | 03 00 00 | Foundation / pier pad and skirting for tiny home (within baseline) | 40 | ea | 6320.3025 | 252812.1
Tiny home pads | Phase 1 | Construction | 06 00 00 | Community building (kitchen, laundry, restrooms/showers, gathering room) (within baseline) | 1 | LS | 421296.9411 | 421296.94
Tiny home pads | Phase 1 | Construction | 32 00 00 | Interior roads / shared drive (20 ft) (within baseline) | 1400 | LF | 102.9814 | 144174
Tiny home pads | Phase 1 | FF&E | 12 00 00 | Furniture, fixtures & equipment | 40 | pad | 468.1037 | 18724.15
Tiny home pads | Phase 1 | Contingency | 99 02 00 | Design contingency | 10 | % of hard |  | 161221.22
Tiny home pads | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 10 | % of hard |  | 179215.76
Tiny home pads | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 7.76 | % of hard |  | 126580.13
Tiny home pads | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 1.19 | % of hard |  | 19473.87
Tiny home pads | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 1.19 | % of hard |  | 19473.86
Tiny home pads | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.84 | % of hard |  | 13631.71
Tiny home pads | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.48 | % of hard |  | 7789.55
Tiny home pads | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.36 | % of hard |  | 5842.16
Tiny home pads | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.96 | % of hard |  | 15579.09
Tiny home pads | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.48 | % of hard |  | 7789.55
Tiny home pads | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.96 | % of hard |  | 15579.09
Tiny home pads | Phase 1 | Soft costs | SC | Owner's representative / project management | 1.79 | % of hard |  | 29210.8
Tiny home pads | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 20500 | 20500
Tiny home pads | Phase 1 | Impact & tap fees | SC | Total impact fees — multifamily unit | 40 | unit | 7874.3 | 314972
Tiny home pads | Phase 1 | Impact & tap fees | SC | Water capacity / tap / impact fee | 24 | EDU | 4838.18 | 116116.32
Tiny home pads | Phase 1 | Impact & tap fees | SC | Sewer (wastewater) capacity / tap / impact fee | 24 | EDU | 4592.44 | 110218.56
Tiny home pads | Phase 1 | Contingency | SC | Soft cost contingency | 5 | % of soft |  | 41137.83
Tiny home pads | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 316666.67
Tiny home pads | Phase 1 | Land | LAND | Land closing costs |  |  |  | 6333.33
Tiny home pads | Phase 1 | Land | LAND | Land due diligence |  |  |  | 32800
Tiny home pads | Phase 1 | Soft costs | SC | Real estate taxes during construction | 1 | years | 3483.3334 | 3483.33
Tiny home pads | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 113550.05
Tiny home pads | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 57417.67
Tiny home pads | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 20315
TOTAL |  |  |  | Total project cost |  |  |  | 3385833.89

## Draws
FINISHES SOLUTIONS
Draw Schedules · Cedar Pines tiny home community · Total $3,385,834
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 713703.05 | 355800 | 1089818.05 | 0 | 0 | 0
2027-04 | 33586.43 | 22268.73 | 0 | 55855.16 | 0 | 0 | 0
2027-05 | 98470.54 | 22268.73 | 0 | 120739.27 | 0 | 0 | 0
2027-06 | 156643.97 | 22268.73 | 0 | 87921.08 | 90991.62 | 0 | 90991.62
2027-07 | 204142.4 | 22268.73 | 0 | 0 | 226411.13 | 530.78 | 317933.53
2027-08 | 237728.84 | 22268.78 | 0 | 0 | 259997.62 | 1854.61 | 579785.76
2027-09 | 255114.47 | 22268.69 | 0 | 0 | 277383.16 | 3382.08 | 860551
2027-10 | 255114.47 | 22268.78 | 0 | 0 | 277383.25 | 5019.88 | 1142954.13
2027-11 | 237728.84 | 22268.69 | 0 | 0 | 259997.53 | 6667.23 | 1409618.89
2027-12 | 204142.4 | 22268.78 | 0 | 0 | 226411.18 | 8222.78 | 1644252.85
2028-01 | 156643.97 | 22268.77 | 0 | 0 | 178912.74 | 9591.47 | 1832757.06
2028-02 | 98470.52 | 22268.69 | 0 | 0 | 120739.21 | 10691.08 | 1964187.35
2028-03 | 33586.47 | 22268.75 | 0 | 0 | 55855.22 | 11457.76 | 2031500.33

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Cedar Pines tiny home community · Total $3,385,834
ASSUMPTIONS
Tiny home pads — baseline price | $48,986 / pad · Derived estimate — verify (specialty-residential/tiny-home-community.json)
Tiny home pads — factors | regional 0.82 · quality 1 · size 0.9894 · escalation 1.0488
Tiny home pads — research note | A tiny home community is priced per pad: utility stubs (water, sewer, 50-100A electric), a foundation or pier/parking pad, roads, landscaping and a share of a community building, with the home itself either owner-supplied (tiny house on wheels) or developer-supplied (optional line item). Published budgets are almost all supportive/transitional villages (Quixote Village WA, Los Angeles tiny home villages), so the market-rate default is derived from those and from the RV park per-site evidence. Confidence low-medium.
Phase 1 — schedule | 2027-03, 12 months, midpoint 2027-09, escalation 4.88% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (42)
Ref | Source | Publisher | Value | Confidence | URL
_common/fees.json#e1 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 13627 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e2 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 6460 USD/unit (2019) | medium | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e3 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 8034 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e9 | It All Adds Up: The Cost of Housing Development Fees in Seven California Cities | Terner Center for Housing Innovation, UC Berkeley (March 2018) | 12000–75000 USD/unit (2018) | high | https://ternercenter.berkeley.edu/wp-content/uploads/2020/08/Development_Fees_Report_Final_2.pdf
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
specialty-residential/rv-park-resort.json#e17 | Bid Tabulation - Campground Development Phase II, Comfort Station - Rebid, Palisades State Park, GFP Project No. Pali23Oa | South Dakota Department of Game, Fish and Parks | 705540 USD/ea (2023) | high | https://gfp.sd.gov/UserDocs/nav/Bid_Tab_Comfort_Station_Rebid.pdf
specialty-residential/rv-park-resort.json#e6 | Lake of the Ozarks State Park - Campground Upgrade Project (revenue bond project sheet) | Missouri State Parks (Missouri DNR) | 55000 USD/site (2020) | high | https://web.archive.org/web/2022id_/https://mostateparks.com/sites/mostateparks/files/LOSP-campground-project.pdf
specialty-residential/rv-park-resort.json#e8 | How much does it cost to build a campground or RV park? | Outdoor Hospitality Weekly (Substack) | 30000–40000 USD/site (2024) | medium | https://ohweekly.substack.com/p/how-much-does-it-cost-to-build-a
specialty-residential/rv-park-resort.json#e9 | How much does it cost to build a campground or RV park? | Outdoor Hospitality Weekly (Substack) | 4000 USD/site (2024) | low | https://ohweekly.substack.com/p/how-much-does-it-cost-to-build-a
specialty-residential/tiny-home-community.json#t1 | Quixote Village 5-Year Report (Department of Commerce transmittal to legislators) | Washington State Department of Commerce / Quixote Communities | 88000 USD/unit (2013) | high | https://www.commerce.wa.gov/wp-content/uploads/2019/04/Commerce-Quixote-Village-5-Year-Report.pdf
specialty-residential/tiny-home-community.json#t2 | What Are the Costs of Building Tiny Home Villages to Decrease Homelessness? | Amark Foundation | 42344 USD/bed (2022) | medium | https://amarkfoundation.org/?p=480
specialty-residential/tiny-home-community.json#t4 | How Much Does a Tiny House Cost? | Bob Vila (BobVila.com) | 45000 USD/unit (2023) | low | https://www.bobvila.com/articles/tiny-house-cost.md