## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Ashley River Marina · Total $21,008,592
COST SUMMARY
Construction hard cost | 11134985.09
FF&E | 0
Design + construction contingency | 2338346.87
Hard cost subtotal | 13473331.96
Soft costs | 2529946.72
Impact & tap fees | 0
Developer fee | 645075.54
Financing (interest + fees) | 630627.52
Soft cost contingency | 123609.84
Soft cost subtotal | 3929259.62
Land & acquisition | 3606000
Total project cost | 21008591.58
BASIS
Location | Charleston, SC (factor 0.900)
Gross building SF | —
Site acres | —
Cost per acre
Research data version | 2026.7c60a42879
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.7c60a42879), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Ashley River Marina · Total $21,008,592
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Marina | Marina | 200 slips | 13473331.96 | 3929259.62 | 3606000 | 21008591.58 | 105042.9579 |  | within ($25,000–$250,000)
Total |  |  | 13473331.96 | 3929259.62 | 3606000 | 21008591.58

## Phases
FINISHES SOLUTIONS
Cost by Phase · Ashley River Marina · Total $21,008,592
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 18 | 2027-12 | 5.9% | 13473331.96 | 3929259.62 | 3606000 | 21008591.58 | 12605154.95 | 504575.97
Total |  |  |  |  | 13473331.96 | 3929259.62 | 3606000 | 21008591.58

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Ashley River Marina · Total $21,008,592
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Marina | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 1109208.89
Marina | Phase 1 | Construction | 02 00 00 | Existing Conditions |  |  |  | 332762.67
Marina | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 332762.67
Marina | Phase 1 | Construction | 10 00 00 | Specialties |  |  |  | 221841.78
Marina | Phase 1 | Construction | 21 00 00 | Fire Suppression |  |  |  | 332762.66
Marina | Phase 1 | Construction | 22 00 00 | Plumbing |  |  |  | 554604.44
Marina | Phase 1 | Construction | 26 00 00 | Electrical — balance |  |  |  | 1091863.54
Marina | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 221841.78
Marina | Phase 1 | Construction | 32 00 00 | Exterior Improvements |  |  |  | 554604.44
Marina | Phase 1 | Construction | 33 00 00 | Utilities |  |  |  | 443683.55
Marina | Phase 1 | Construction | 35 00 00 | Waterway & Marine Construction — balance |  |  |  | 5038227.76
Marina | Phase 1 | Construction | 26 00 00 | Utility pedestals (power + water, lighting) per slip (within baseline) | 100 | ea | 5719.4979 | 571949.79
Marina | Phase 1 | Construction | 35 00 00 | ADA gangway (80-120 ft aluminum) with abutment and landing float (within baseline) | 1 | ea | 285974.8941 | 285974.89
Marina | Phase 1 | Specialty & site | 22 00 00 | Sewage pump-out station (fixed) incl. piping to sanitary | 1 | ea | 42896.2341 | 42896.23
Marina | Phase 1 | Contingency | 99 02 00 | Design contingency | 10 | % of hard |  | 1113498.51
Marina | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 10 | % of hard |  | 1224848.36
Marina | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 10.67 | % of hard |  | 1188285.72
Marina | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 1.64 | % of hard |  | 182813.19
Marina | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 1.64 | % of hard |  | 182813.19
Marina | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 1.15 | % of hard |  | 127969.23
Marina | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.66 | % of hard |  | 73125.28
Marina | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.49 | % of hard |  | 54843.96
Marina | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 1.31 | % of hard |  | 146250.55
Marina | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.66 | % of hard |  | 73125.27
Marina | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 1.31 | % of hard |  | 146250.55
Marina | Phase 1 | Soft costs | SC | Owner's representative / project management | 2.46 | % of hard |  | 274219.78
Marina | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 22500 | 22500
Marina | Phase 1 | Contingency | SC | Soft cost contingency | 5 | % of soft |  | 123609.84
Marina | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 3500000
Marina | Phase 1 | Land | LAND | Land closing costs |  |  |  | 70000
Marina | Phase 1 | Land | LAND | Land due diligence |  |  |  | 36000
Marina | Phase 1 | Soft costs | SC | Real estate taxes during construction | 1.5 | years | 38500 | 57750
Marina | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 645075.54
Marina | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 504575.97
Marina | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 126051.55
TOTAL |  |  |  | Total project cost |  |  |  | 21008591.58

## Draws
FINISHES SOLUTIONS
Draw Schedules · Ashley River Marina · Total $21,008,592
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 1448442.87 | 3606000 | 5180494.42 | 0 | 0 | 0
2027-04 | 102345.11 | 102788.28 | 0 | 205133.39 | 0 | 0 | 0
2027-05 | 303925.6 | 102788.28 | 0 | 406713.88 | 0 | 0 | 0
2027-06 | 496271.44 | 102788.28 | 0 | 599059.72 | 0 | 0 | 0
2027-07 | 673538.3 | 102788.28 | 0 | 776326.58 | 0 | 0 | 0
2027-08 | 830340.13 | 102788.35 | 0 | 933128.48 | 0 | 0 | 0
2027-09 | 961912.41 | 102788.27 | 0 | 302580.16 | 762120.52 | 0 | 762120.52
2027-10 | 1064257.52 | 102788.32 | 0 | 0 | 1167045.84 | 4445.7 | 1933612.06
2027-11 | 1134265.7 | 102788.27 | 0 | 0 | 1237053.97 | 11279.4 | 3181945.43
2027-12 | 1169809.76 | 102788.32 | 0 | 0 | 1272598.08 | 18561.35 | 4473104.86
2028-01 | 1169809.76 | 102788.32 | 0 | 0 | 1272598.08 | 26093.11 | 5771796.05
2028-02 | 1134265.7 | 102788.3 | 0 | 0 | 1237054 | 33668.81 | 7042518.86
2028-03 | 1064257.51 | 102788.27 | 0 | 0 | 1167045.78 | 41081.36 | 8250646
2028-04 | 961912.41 | 102788.3 | 0 | 0 | 1064700.71 | 48128.77 | 9363475.48
2028-05 | 830340.13 | 102788.28 | 0 | 0 | 933128.41 | 54620.27 | 10351224.16
2028-06 | 673538.35 | 102788.28 | 0 | 0 | 776326.63 | 60382.14 | 11187932.93
2028-07 | 496271.44 | 102788.27 | 0 | 0 | 599059.71 | 65262.94 | 11852255.58
2028-08 | 303925.6 | 102788.28 | 0 | 0 | 406713.88 | 69138.16 | 12328107.62
2028-09 | 102345.09 | 102788.28 | 0 | 0 | 205133.37 | 71913.96 | 12605154.95

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Ashley River Marina · Total $21,008,592
ASSUMPTIONS
Marina — baseline price | $60,000 / slip · Researched (marine-other/marina.json)
Marina — factors | regional 0.9 · quality 1 · size 0.9772 · escalation 1.0592
Marina — research note | Per-slip cost is driven by slip length/vessel class, dock system (timber vs. concrete floats, steel vs. concrete piles), utilities (power, water, fire suppression, pump-out) and exposure (wave attenuation). Site-specific heavy items — dredging, breakwaters, bulkheads, fuel systems — vary by orders of magnitude and are carried as separate line items. Evidence is a set of recent public project budgets (USFWS Boating Infrastructure Grant FY2025-26 summaries, Treasure Island, Berkeley); these are total project costs for transient facilities, so the default is medium confidence.
Phase 1 — schedule | 2027-03, 18 months, midpoint 2027-12, escalation 5.92% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (43)
Ref | Source | Publisher | Value | Confidence | URL
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
marine-other/marina.json#e1 | FY 2026 Boating Infrastructure Grant Program, Tier 2 — funded application summaries | U.S. Fish and Wildlife Service | 75000 USD/slip (2026) | medium | https://www.fws.gov/sites/default/files/documents/2026-06/fy-2026-big-tier-2-funded-application-summaries.pdf
marine-other/marina.json#e10 | Construction Contract: The Dutra Group for the Docks D & E Replacement Project at the Berkeley Marina (Council report, May 7, 2024) | City of Berkeley | 7812000 USD/ls (2024) | high | https://berkeleyca.gov/sites/default/files/documents/2024-05-07%20Item%2005%20Construction%20Contract%20%20THE%20DUTRA%20GROUP.pdf
marine-other/marina.json#e11 | FY 2026 Boating Infrastructure Grant Program, Tier 2 — funded application summaries | U.S. Fish and Wildlife Service | 2001 USD/lf (2026) | medium | https://www.fws.gov/sites/default/files/documents/2026-06/fy-2026-big-tier-2-funded-application-summaries.pdf
marine-other/marina.json#e12 | $6.2 Million Grant Awarded for Westport Marina Modernization | Marina Dock Age | 8800000 USD/ls (2026) | low | https://www.marinadockage.com/6-2-million-grant-awarded-for-westport-marina-modernization/
marine-other/marina.json#e2 | FY 2026 Boating Infrastructure Grant Program, Tier 2 — funded application summaries | U.S. Fish and Wildlife Service | 78920 USD/slip (2026) | medium | https://www.fws.gov/sites/default/files/documents/2026-06/fy-2026-big-tier-2-funded-application-summaries.pdf
marine-other/marina.json#e3 | FY 2026 Boating Infrastructure Grant Program, Tier 2 — funded application summaries | U.S. Fish and Wildlife Service | 61627 USD/slip (2026) | medium | https://www.fws.gov/sites/default/files/documents/2026-06/fy-2026-big-tier-2-funded-application-summaries.pdf
marine-other/marina.json#e4 | FY 2026 Boating Infrastructure Grant Program, Tier 2 — funded application summaries | U.S. Fish and Wildlife Service | 26622 USD/slip (2026) | medium | https://www.fws.gov/sites/default/files/documents/2026-06/fy-2026-big-tier-2-funded-application-summaries.pdf
marine-other/marina.json#e5 | FY 2026 Boating Infrastructure Grant Program, Tier 2 — funded application summaries | U.S. Fish and Wildlife Service | 53023 USD/slip (2026) | medium | https://www.fws.gov/sites/default/files/documents/2026-06/fy-2026-big-tier-2-funded-application-summaries.pdf
marine-other/marina.json#e6 | Boating Infrastructure Grant Program, FY 2025 — Tier 2 application summaries | U.S. Fish and Wildlife Service | 100375 USD/slip (2025) | medium | https://www.fws.gov/sites/default/files/documents/2025-05/fy-2025-big-tier-2-application-summaries.pdf
marine-other/marina.json#e7 | Boating Infrastructure Grant Program, FY 2025 — Tier 2 application summaries | U.S. Fish and Wildlife Service | 175289 USD/slip (2025) | medium | https://www.fws.gov/sites/default/files/documents/2025-05/fy-2025-big-tier-2-application-summaries.pdf
marine-other/marina.json#e8 | Boating Infrastructure Grant Program, FY 2025 — Tier 2 application summaries | U.S. Fish and Wildlife Service | 78300 USD/slip (2025) | medium | https://www.fws.gov/sites/default/files/documents/2025-05/fy-2025-big-tier-2-application-summaries.pdf
marine-other/marina.json#e9 | $25M Treasure Island marina project moves forward after new funding partnership | Local News Matters (Bay City News) | 148810 USD/slip (2025) | low | https://localnewsmatters.org/2025/10/14/25m-treasure-island-marina-project-moves-forward-after-new-funding-partnership/