## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Bayside Climate Storage · Total $17,701,929
COST SUMMARY
Construction hard cost | 10194883.77
FF&E | 0
Design + construction contingency | 1044975.59
Hard cost subtotal | 11239859.36
Soft costs | 2091026.75
Impact & tap fees | 693984
Developer fee | 568706.59
Financing (interest + fees) | 433557.06
Soft cost contingency | 192794.75
Soft cost subtotal | 3980069.15
Land & acquisition | 2482000
Total project cost | 17701928.51
BASIS
Location | Tampa, FL (factor 0.850)
Gross building SF | 117,040
Site acres | 2.32
Cost per acre | 7644014.5839
Research data version | 2026.0c737c8255
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.0c737c8255), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Bayside Climate Storage · Total $17,701,929
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
Climate-controlled storage | Self-storage — climate controlled | 88000 NRSF | 11239859.36 | 3980069.15 | 2482000 | 17701928.51 | 201.1583 | 151.2468 | within ($85–$280)
Total |  |  | 11239859.36 | 3980069.15 | 2482000 | 17701928.51

## Phases
FINISHES SOLUTIONS
Cost by Phase · Bayside Climate Storage · Total $17,701,929
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 14 | 2027-10 | 5.2% | 11239859.36 | 3980069.15 | 2482000 | 17701928.51 | 10621157.11 | 327345.49
Total |  |  |  |  | 11239859.36 | 3980069.15 | 2482000 | 17701928.51

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Bayside Climate Storage · Total $17,701,929
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
Climate-controlled storage | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 886677.56
Climate-controlled storage | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 1379276.21
Climate-controlled storage | Phase 1 | Construction | 05 00 00 | Metals |  |  |  | 1379276.21
Climate-controlled storage | Phase 1 | Construction | 07 00 00 | Thermal & Moisture Protection |  |  |  | 689638.1
Climate-controlled storage | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 886677.56
Climate-controlled storage | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 591118.38
Climate-controlled storage | Phase 1 | Construction | 14 00 00 | Conveying Equipment — balance |  |  |  | 96760.75
Climate-controlled storage | Phase 1 | Construction | 21 00 00 | Fire Suppression |  |  |  | 394078.91
Climate-controlled storage | Phase 1 | Construction | 22 00 00 | Plumbing |  |  |  | 197039.46
Climate-controlled storage | Phase 1 | Construction | 23 00 00 | HVAC |  |  |  | 689638.1
Climate-controlled storage | Phase 1 | Construction | 26 00 00 | Electrical |  |  |  | 591118.38
Climate-controlled storage | Phase 1 | Construction | 27 00 00 | Communications |  |  |  | 98519.73
Climate-controlled storage | Phase 1 | Construction | 28 00 00 | Electronic Safety & Security — balance |  |  |  | 127892.18
Climate-controlled storage | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 295559.18
Climate-controlled storage | Phase 1 | Construction | 32 00 00 | Exterior Improvements |  |  |  | 394078.91
Climate-controlled storage | Phase 1 | Construction | 33 00 00 | Utilities |  |  |  | 197039.45
Climate-controlled storage | Phase 1 | Construction | 14 00 00 | Freight/passenger elevators (hydraulic or MRL) (within baseline) | 2 | ea | 102858.9342 | 205717.87
Climate-controlled storage | Phase 1 | Construction | 10 00 00 | Steel unit partitions, corridor system and roll-up unit doors (within baseline) | 88000 | NRSF | 11.6275 | 1023222.79
Climate-controlled storage | Phase 1 | Construction | 28 00 00 | Gate/keypad access control, door alarms, CCTV and kiosk (within baseline) | 1 | LS | 71554.0412 | 71554.04
Climate-controlled storage | Phase 1 | Contingency | 99 02 00 | Design contingency | 5 | % of hard |  | 509744.19
Climate-controlled storage | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 5 | % of hard |  | 535231.4
Climate-controlled storage | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 9.7 | % of hard |  | 989055.89
Climate-controlled storage | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 1.49 | % of hard |  | 152162.44
Climate-controlled storage | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 1.49 | % of hard |  | 152162.44
Climate-controlled storage | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 1.04 | % of hard |  | 106513.71
Climate-controlled storage | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.6 | % of hard |  | 60864.98
Climate-controlled storage | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.45 | % of hard |  | 45648.73
Climate-controlled storage | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 1.19 | % of hard |  | 121729.96
Climate-controlled storage | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.6 | % of hard |  | 60864.98
Climate-controlled storage | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 1.19 | % of hard |  | 121729.95
Climate-controlled storage | Phase 1 | Soft costs | SC | Owner's representative / project management | 2.24 | % of hard |  | 228243.67
Climate-controlled storage | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 21250 | 21250
Climate-controlled storage | Phase 1 | Impact & tap fees | SC | Total impact fees — industrial | 117.04 | 1,000 SF | 4225.85 | 494593.48
Climate-controlled storage | Phase 1 | Impact & tap fees | SC | Water capacity / tap / impact fee | 29.26 | EDU | 3407.22 | 99695.26
Climate-controlled storage | Phase 1 | Impact & tap fees | SC | Sewer (wastewater) capacity / tap / impact fee | 29.26 | EDU | 3407.22 | 99695.26
Climate-controlled storage | Phase 1 | Contingency | SC | Soft cost contingency | 7 | % of soft |  | 192794.75
Climate-controlled storage | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 2400000
Climate-controlled storage | Phase 1 | Land | LAND | Land closing costs |  |  |  | 48000
Climate-controlled storage | Phase 1 | Land | LAND | Land due diligence |  |  |  | 34000
Climate-controlled storage | Phase 1 | Soft costs | SC | Real estate taxes during construction | 1.17 | years | 26400 | 30800
Climate-controlled storage | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 568706.59
Climate-controlled storage | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 327345.49
Climate-controlled storage | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 106211.57
TOTAL |  |  |  | Total project cost |  |  |  | 17701928.51

## Draws
FINISHES SOLUTIONS
Draw Schedules · Bayside Climate Storage · Total $17,701,929
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 1902101.06 | 2482000 | 4490312.63 | 0 | 0 | 0
2027-04 | 140903.38 | 117457.95 | 0 | 258361.33 | 0 | 0 | 0
2027-05 | 415644.6 | 117457.94 | 0 | 533102.54 | 0 | 0 | 0
2027-06 | 669543.7 | 117457.94 | 0 | 787001.64 | 0 | 0 | 0
2027-07 | 889869.14 | 117457.93 | 0 | 1007327.07 | 0 | 0 | 0
2027-08 | 1065572.75 | 117457.95 | 0 | 4666.19 | 1178364.51 | 0 | 1178364.51
2027-09 | 1187844.11 | 117457.93 | 0 | 0 | 1305302.04 | 6873.79 | 2490540.34
2027-10 | 1250551.98 | 117457.95 | 0 | 0 | 1368009.93 | 14528.15 | 3873078.42
2027-11 | 1250552.03 | 117457.92 | 0 | 0 | 1368009.95 | 22592.96 | 5263681.33
2027-12 | 1187844.1 | 117457.96 | 0 | 0 | 1305302.06 | 30704.81 | 6599688.2
2028-01 | 1065572.73 | 117457.91 | 0 | 0 | 1183030.64 | 38498.18 | 7821217.02
2028-02 | 889869.14 | 117457.91 | 0 | 0 | 1007327.05 | 45623.77 | 8874167.84
2028-03 | 669543.7 | 117457.91 | 0 | 0 | 787001.61 | 51765.98 | 9712935.43
2028-04 | 415644.6 | 117457.95 | 0 | 0 | 533102.55 | 56658.79 | 10302696.77
2028-05 | 140903.4 | 117457.88 | 0 | 0 | 258361.28 | 60099.06 | 10621157.11

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Bayside Climate Storage · Total $17,701,929
ASSUMPTIONS
Climate-controlled storage — baseline price | $130 / NRSF · Derived estimate — verify (industrial/self-storage-climate.json)
Climate-controlled storage — factors | regional 0.85 · quality 1 · size 0.9972 · escalation 1.0523
Climate-controlled storage — research note | Multi-story (typically 3–5 stories) interior-access climate-controlled storage on 1.5–4 acre infill sites. Cost drivers: structural system (steel/PEMB vs. concrete podium), number of stories and elevators, unit-mix partitions and roll-up doors, HVAC, and efficiency (rentable vs gross area ≈ 70–80%). Public evidence is a scatter of announced project costs (Inside Self Storage roundups) whose scope (construction vs total, gross vs rentable) is unclear, plus one vendor cost table; the default is a reasoned midpoint, medium-low confidence.
Phase 1 — schedule | 2027-03, 14 months, midpoint 2027-10, escalation 5.23% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (46)
Ref | Source | Publisher | Value | Confidence | URL
_blocks/building-systems.json#e1 | How Much Does Elevator Installation Cost? | ThePricer | 75000–350000 USD/ea (2026) | low | https://www.thepricer.org/elevator-installation-costs/
_blocks/building-systems.json#e7 | Key Card Door Lock System Price: Overview & Guide (2026) | Safe and Sound Security | 1500–4500 USD/ea (2026) | low | https://getsafeandsound.com/blog/key-card-door-lock-system-price/
_common/fees.json#e1 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 13627 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e2 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 6460 USD/unit (2019) | medium | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e6 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 3942 USD/1000sf (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
industrial/self-storage-climate.json#e1 | Self Storage Building Costs in 2026: A Comprehensive Guide | Storeganise | 105–175 USD/sf (2026) | low | https://storeganise.com/blog/Self-Storage-Building-Costs
industrial/self-storage-climate.json#e2 | Self Storage Building Costs in 2026: A Comprehensive Guide | Storeganise | 80–125 USD/sf (2026) | low | https://storeganise.com/blog/Self-Storage-Building-Costs
industrial/self-storage-climate.json#e3 | Self Storage Building Costs in 2026: A Comprehensive Guide | Storeganise | 0.15–0.22 pct (2026) | low | https://storeganise.com/blog/Self-Storage-Building-Costs
industrial/self-storage-climate.json#e4 | Self-Storage Development and Zoning Activity: March 2025 | Inside Self Storage (Informa) | 55.45 USD/sf (2025) | medium | https://www.insideselfstorage.com/self-storage-development/self-storage-development-and-zoning-activity-march-2025
industrial/self-storage-climate.json#e5 | Self-Storage Development and Zoning Activity: March 2025 | Inside Self Storage (Informa) | 185.71 USD/sf (2025) | medium | https://www.insideselfstorage.com/self-storage-development/self-storage-development-and-zoning-activity-march-2025
industrial/self-storage-climate.json#e6 | Self-Storage Development and Zoning Activity: October 2026 | Inside Self Storage (Informa) | 58 USD/sf (2026) | medium | https://www.insideselfstorage.com/self-storage-development/self-storage-development-and-zoning-activity-october-2026
industrial/self-storage-climate.json#e7 | Self-Storage Development and Zoning Activity: July 2026 | Inside Self Storage (Informa) | 149.83 USD/sf (2026) | medium | https://www.insideselfstorage.com/self-storage-development/self-storage-development-and-zoning-activity-july-2026
industrial/self-storage-climate.json#e8 | Self-Storage Development and Zoning Activity: August 2026 | Inside Self Storage (Informa) | 134.68 USD/sf (2026) | medium | https://www.insideselfstorage.com/self-storage-development/self-storage-development-and-zoning-activity-august-2026
industrial/self-storage-climate.json#e9 | Self-Storage Development and Zoning Activity: October 2026 | Inside Self Storage (Informa) | 204.37 USD/sf (2026) | low | https://www.insideselfstorage.com/self-storage-development/self-storage-development-and-zoning-activity-october-2026
residential/single-family.json#e10 | Cost of Constructing a Home-2024 (Special Study for Housing Economics) | National Association of Home Builders (Eric Lynch) | 26747 USD/unit (2024) | high | https://nahb.org/-/media/AB4EFC742624475A97A0A62189986FF8.ashx