## Estimate Summary
FINISHES SOLUTIONS
Total Project Cost — Summary · Gulf Breeze RV Resort · Total $9,487,485
COST SUMMARY
Construction hard cost | 5476398.82
FF&E | 224223.98
Design + construction contingency | 1172466.15
Hard cost subtotal | 6873088.95
Soft costs | 714762.24
Impact & tap fees | 503557.5
Developer fee | 326075.11
Financing (interest + fees) | 209732.56
Soft cost contingency | 60469.11
Soft cost subtotal | 1814596.52
Land & acquisition | 799800
Total project cost | 9487485.47
BASIS
Location | Florida (factor 0.870)
Gross building SF | —
Site acres | 12.50
Cost per acre | 758998.8376
Research data version | 2026.0c737c8255
Engine | budget-engine-2.0.0
All defaults come from the research data shipped with the app (2026.0c737c8255), escalated to the construction midpoint and adjusted to the project location. Values marked "Derived estimate — verify" have no direct published source.

## Components
FINISHES SOLUTIONS
Cost by Component · Gulf Breeze RV Resort · Total $9,487,485
Component | Type | Size | Hard (incl. FF&E, cont.) | Soft (incl. fin.) | Land | Total | Per primary unit | Per SF | Range check
RV resort | RV park / resort | 150 sites | 6873088.95 | 1814596.52 | 799800 | 9487485.47 | 63249.9031 |  | within ($19,594–$152,400)
Total |  |  | 6873088.95 | 1814596.52 | 799800 | 9487485.47

## Phases
FINISHES SOLUTIONS
Cost by Phase · Gulf Breeze RV Resort · Total $9,487,485
Phase | Start | Months | Midpoint | Escalation | Hard | Soft | Land | Total | Loan | Interest
Phase 1 | 2027-03 | 13 | 2027-10 | 5.2% | 6873088.95 | 1814596.52 | 799800 | 9487485.47 | 5692491.28 | 152807.65
Total |  |  |  |  | 6873088.95 | 1814596.52 | 799800 | 9487485.47

## Detail
FINISHES SOLUTIONS
Line-Item Detail · Gulf Breeze RV Resort · Total $9,487,485
Component | Phase | Group | Code | Line | Qty | Unit | Rate | Amount | Edited
RV resort | Phase 1 | Construction | 01 00 00 | General Requirements |  |  |  | 314847.59
RV resort | Phase 1 | Construction | 03 00 00 | Concrete |  |  |  | 157423.79
RV resort | Phase 1 | Construction | 07 00 00 | Thermal & Moisture Protection |  |  |  | 118067.84
RV resort | Phase 1 | Construction | 08 00 00 | Openings |  |  |  | 59033.92
RV resort | Phase 1 | Construction | 09 00 00 | Finishes |  |  |  | 98389.87
RV resort | Phase 1 | Construction | 10 00 00 | Specialties |  |  |  | 59033.92
RV resort | Phase 1 | Construction | 23 00 00 | HVAC |  |  |  | 47227.14
RV resort | Phase 1 | Construction | 26 00 00 | Electrical — balance |  |  |  | 269892.2
RV resort | Phase 1 | Construction | 31 00 00 | Earthwork |  |  |  | 287298.42
RV resort | Phase 1 | Construction | 32 00 00 | Exterior Improvements — balance |  |  |  | 607918.63
RV resort | Phase 1 | Construction | 33 00 00 | Utilities — balance |  |  |  | 31017.38
RV resort | Phase 1 | Construction | 26 00 00 | RV power pedestal (50/30/20A) incl. setting and connection (within baseline) | 150 | ea | 1913.9199 | 287087.99
RV resort | Phase 1 | Construction | 33 00 00 | Water and sewer hookups per site (riser, hose bib, 4in sewer inlet, laterals) (within baseline) | 150 | ea | 4883.1122 | 732466.83
RV resort | Phase 1 | Construction | 32 00 00 | RV pad and patio (gravel, asphalt or concrete pad; concrete patio) (within baseline) | 150 | ea | 3188.9694 | 478345.41
RV resort | Phase 1 | Construction | 32 00 00 | Interior park roads (20-24 ft, gravel to asphalt) (within baseline) | 6000 | LF | 99.6582 | 597948.92
RV resort | Phase 1 | Construction | 22 00 00 | Bathhouse / comfort station with showers and laundry (within baseline) | 1 | ea | 697587.4838 | 697587.48
RV resort | Phase 1 | Construction | 06 00 00 | Office / camp store / clubhouse (within baseline) | 1 | LS | 597932.1225 | 597932.12
RV resort | Phase 1 | Construction | 33 00 00 | RV dump (sanitary) station with rinse water (within baseline) | 1 | ea | 34879.3742 | 34879.37
RV resort | Phase 1 | FF&E | 12 00 00 | Furniture, fixtures & equipment | 150 | site | 1494.8265 | 224223.98
RV resort | Phase 1 | Contingency | 99 02 00 | Design contingency | 10 | % of hard |  | 547639.88
RV resort | Phase 1 | Contingency | 99 03 00 | Hard cost (construction) contingency | 10 | % of hard |  | 624826.27
RV resort | Phase 1 | Soft costs | SC | Architecture & engineering (basic services, design + CA) | 5.82 | % of hard |  | 331827.3
RV resort | Phase 1 | Soft costs | SC | Civil engineering, ALTA/topo survey, geotechnical report | 0.9 | % of hard |  | 51050.36
RV resort | Phase 1 | Soft costs | SC | Building permit & plan review fees (excl. impact / tap fees) | 0.9 | % of hard |  | 51050.35
RV resort | Phase 1 | Soft costs | SC | Legal, accounting, cost certification | 0.63 | % of hard |  | 35735.25
RV resort | Phase 1 | Soft costs | SC | Builder's risk insurance | 0.36 | % of hard |  | 20420.14
RV resort | Phase 1 | Soft costs | SC | Owner's general liability / OCIP-OCP during construction | 0.27 | % of hard |  | 15315.11
RV resort | Phase 1 | Soft costs | SC | Marketing, lease-up / rent-up (excl. commercial leasing commissions) | 0.72 | % of hard |  | 40840.28
RV resort | Phase 1 | Soft costs | SC | Construction-loan title, closing & recording | 0.36 | % of hard |  | 20420.14
RV resort | Phase 1 | Soft costs | SC | Special inspections, materials testing, commissioning | 0.72 | % of hard |  | 40840.28
RV resort | Phase 1 | Soft costs | SC | Owner's representative / project management | 1.34 | % of hard |  | 76575.53
RV resort | Phase 1 | Soft costs | SC | Third-party reports (appraisal, Phase I ESA, market study, PCA/CNA) | 1 | project | 21750 | 21750
RV resort | Phase 1 | Impact & tap fees | SC | Total impact fees — hotel room | 150 | unit | 3357.05 | 503557.5
RV resort | Phase 1 | Contingency | SC | Soft cost contingency | 5 | % of soft |  | 60469.11
RV resort | Phase 1 | Land | LAND | Land / acquisition |  |  |  | 750000
RV resort | Phase 1 | Land | LAND | Land closing costs |  |  |  | 15000
RV resort | Phase 1 | Land | LAND | Land due diligence |  |  |  | 34800
RV resort | Phase 1 | Soft costs | SC | Real estate taxes during construction | 1.08 | years | 8250 | 8937.5
RV resort | Phase 1 | Developer fee | DEV | Developer fee | 4 | % of cost excl. land |  | 326075.11
RV resort | Phase 1 | Financing | FIN | Construction loan interest (capitalized) |  |  |  | 152807.65
RV resort | Phase 1 | Financing | FIN | Construction loan fee |  |  |  | 56924.91
TOTAL |  |  |  | Total project cost |  |  |  | 9487485.47

## Draws
FINISHES SOLUTIONS
Draw Schedules · Gulf Breeze RV Resort · Total $9,487,485
PHASE 1 — MONTHLY DRAWS
Month | Hard | Soft | Land | Equity | Loan draw | Interest | Loan balance
2027-03 | 0 | 923500.27 | 799800 | 1780225.18 | 0 | 0 | 0
2027-04 | 99859.76 | 52412.6 | 0 | 152272.36 | 0 | 0 | 0
2027-05 | 293775.71 | 52412.59 | 0 | 346188.3 | 0 | 0 | 0
2027-06 | 470618.54 | 52412.59 | 0 | 523031.13 | 0 | 0 | 0
2027-07 | 620110.7 | 52412.59 | 0 | 672523.29 | 0 | 0 | 0
2027-08 | 733564.31 | 52412.58 | 0 | 320753.93 | 465222.96 | 0 | 465222.96
2027-09 | 804385.79 | 52412.58 | 0 | 0 | 856798.37 | 2713.8 | 1324735.13
2027-10 | 828459.33 | 52412.58 | 0 | 0 | 880871.91 | 7727.62 | 2213334.66
2027-11 | 804385.79 | 52412.62 | 0 | 0 | 856798.41 | 12911.12 | 3083044.19
2027-12 | 733564.27 | 52412.58 | 0 | 0 | 785976.85 | 17984.42 | 3887005.46
2028-01 | 620110.73 | 52412.61 | 0 | 0 | 672523.34 | 22674.2 | 4582203
2028-02 | 470618.53 | 52412.58 | 0 | 0 | 523031.11 | 26729.52 | 5131963.63
2028-03 | 293775.74 | 52412.61 | 0 | 0 | 346188.35 | 29936.45 | 5508088.43
2028-04 | 99859.75 | 52412.58 | 0 | 0 | 152272.33 | 32130.52 | 5692491.28

## Sources
FINISHES SOLUTIONS
Sources & Assumptions · Gulf Breeze RV Resort · Total $9,487,485
ASSUMPTIONS
RV resort — baseline price | $45,720 / site · Researched (specialty-residential/rv-park-resort.json)
RV resort — factors | regional 0.87 · quality 1 · size 0.9681 · escalation 1.0523
RV resort — research note | Cost per site is driven by wastewater (municipal sewer vs. septic/drainfield vs. package plant), electrical service (50A pedestals and distribution), road and pad surfacing (gravel vs. asphalt/concrete) and how much building (bathhouse, clubhouse, store, pool) is spread over the sites. Public-sector bid-grade evidence (Missouri, Utah state parks) runs $50k-$112k per site; private-developer itemizations run roughly $15k-$40k per site. The default sits between them, weighted toward private development; confidence is medium.
Phase 1 — schedule | 2027-03, 13 months, midpoint 2027-10, escalation 5.23% (forecast rates from _indices/escalation.json)
Phase 1 — financing | LTC 60%, rate 7.00%, fee 1.00%
SOURCES (51)
Ref | Source | Publisher | Value | Confidence | URL
_common/fees.json#e3 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 8034 USD/unit (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/fees.json#e5 | National Impact Fee Survey: 2019 | Duncan Associates (Clancy Mullen) | 5408 USD/1000sf (2019) | high | https://www.impactfees.com/publications%20pdf/2019survey.pdf
_common/financing.json#e1 | Secured Overnight Financing Rate (SOFR) | Federal Reserve Bank of St. Louis (FRED) | 0.039 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR
_common/financing.json#e2 | 30-Day Average SOFR (SOFR30DAYAVG) | Federal Reserve Bank of St. Louis (FRED) | 0.03889 pct (2026) | high | https://fred.stlouisfed.org/series/SOFR30DAYAVG
_common/financing.json#e3 | Bank Prime Loan Rate (DPRIME) | Federal Reserve Bank of St. Louis (FRED) | 0.07 pct (2026) | high | https://fred.stlouisfed.org/series/DPRIME
_common/financing.json#e4 | Federal Funds Target Range - Upper Limit (DFEDTARU) | Federal Reserve Bank of St. Louis (FRED) | 0.0375–0.04 pct (2026) | high | https://fred.stlouisfed.org/series/DFEDTARU
_common/financing.json#e5 | 12 CFR Appendix A to Subpart A of Part 365 - Interagency Guidelines for Real Estate Lending Policies | Legal Information Institute, Cornell Law School (text of FDIC regulation) | 0.8 pct | high | https://www.law.cornell.edu/cfr/text/12/appendix-A_to_subpart_A_of_part_365
_common/financing.json#e6 | The July 2026 Senior Loan Officer Opinion Survey on Bank Lending Practices | Board of Governors of the Federal Reserve System | text (2026) | high | https://www.federalreserve.gov/data/sloos/sloos-202607.htm
_common/land-closing.json#e1 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 5226 USD/policy (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/land-closing.json#e2 | Real estate excise tax | Washington State Department of Revenue | 0.0128 pct (2026) | high | https://dor.wa.gov/taxes-rates/other-taxes/real-estate-excise-tax
_common/land-closing.json#e3 | Realty Transfer Tax | Pennsylvania Department of Revenue | 0.01 pct (2026) | high | https://www.pa.gov/en/agencies/revenue/resources/tax-types-and-information/realty-transfer-tax.html
_common/land-closing.json#e4 | Documentary Stamp Tax | Florida Department of Revenue | 0.007 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/land-closing.json#e5 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e1 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0852 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e10 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0035–0.009 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e11 | Builders Risk Insurance in 2026: What It Costs, Who Pays, and the Exclusions That Wreck Commercial Projects | Terrapin Construction Group | 0.0007–0.0019 pct (2026) | low | https://terrapincg.com/news/builders-risk-insurance-commercial-construction-cost-2026
_common/soft-costs.json#e13 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | text (2025) | medium | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e14 | What are Typical Developer Fees on a Multifamily Development? | HelloData | 0.03–0.05 pct (2025) | low | https://www.hellodata.ai/help-articles/what-are-typical-developer-fees-on-a-multifamily-development
_common/soft-costs.json#e15 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 0.15 pct (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e16 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.15 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e17 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 1200 USD/unit (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e18 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 500 USD/unit (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
_common/soft-costs.json#e19 | Title Rate Chart (effective March 1, 2026) | Texas Department of Insurance | 0.005226 pct (2026) | high | https://www.tdi.texas.gov/title/titlerates2026.html
_common/soft-costs.json#e2 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0988 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e20 | Documentary Stamp Tax | Florida Department of Revenue | 0.0035 pct (2026) | high | https://floridarevenue.com/taxes/taxesfees/Pages/doc_stamp.aspx
_common/soft-costs.json#e21 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.01 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e3 | Chapter 08: Architect/Engineer Fee Guidelines and Fee Schedule (2027-29 capital budget instructions) | Washington State Office of Financial Management | 0.0716 pct (2026) | high | https://ofm.wa.gov/budget/state-budget-2027-29/instructions/capital/chapter-08/
_common/soft-costs.json#e4 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 0.0483 pct (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e5 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.06 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e6 | Board of Commissioners agenda item — Edneyville Elementary School proposal (Feb 15, 2017) | Henderson County, North Carolina | 0.12 pct (2017) | high | https://www.hendersoncountync.gov/sites/default/files/archives/Meetings/Board_of_Commissioners/agenda170215/DI.B.pdf
_common/soft-costs.json#e7 | Building Valuation Data – August 2025 | International Code Council (posted by City of Kirkland, WA) | 0.0075 pct (2025) | low | https://www.kirklandwa.gov/files/sharedassets/public/v/2/development-services/pdfs/building-pdfs/icc-august-2025.pdf
_common/soft-costs.json#e8 | PHFA 2025 Underwriting Application — Development Cost Limits (revised 1-17-25) | Pennsylvania Housing Finance Agency | 175000 USD/project (2025) | high | https://www.phfa.org/forms/multifamily_application_guidelines/application/2025-2026-mai-07.pdf
_common/soft-costs.json#e9 | 2025-2026 Delaware State Housing Authority Low Income Housing Tax Credit Guidelines | Delaware State Housing Authority | 150000 USD/project (2025) | high | https://www.destatehousing.com/wp-content/uploads/2026/06/2025-2026-LIHTC-Guidelines.pdf
specialty-residential/rv-park-resort.json#e1 | Lake of the Ozarks State Park - Campground Upgrade Project (revenue bond project sheet) | Missouri State Parks (Missouri DNR) | 78622 USD/site (2020) | high | https://web.archive.org/web/2022id_/https://mostateparks.com/sites/mostateparks/files/LOSP-campground-project.pdf
specialty-residential/rv-park-resort.json#e10 | How much does it cost to build a campground or RV park? | Outdoor Hospitality Weekly (Substack) | 5000–10000 USD/site (2024) | low | https://ohweekly.substack.com/p/how-much-does-it-cost-to-build-a
specialty-residential/rv-park-resort.json#e11 | Campgrounds - Freakonomics | Freakonomics Radio Network - The Economics of Everyday Things, Ep. 112 (Oct 26, 2025) | 15000–25000 USD/site (2025) | low | https://freakonomics.com/podcast/campgrounds/
specialty-residential/rv-park-resort.json#e12 | Menahga City Council Advances Plans for 10 Permanent Campsites at Memorial Forest Park | Modern Campground | 9200 USD/site (2025) | low | https://moderncampground.com/?p=68943
specialty-residential/rv-park-resort.json#e13 | Menahga City Council Advances Plans for 10 Permanent Campsites at Memorial Forest Park | Modern Campground | 500–600 USD/ea (2025) | low | https://moderncampground.com/?p=68943
specialty-residential/rv-park-resort.json#e16 | Oregon State Parks and Recreation Commission, Nov. 20, 2024, Agenda Item 8d - Ft. Stevens Utility Upgrade Construction Contract | Oregon Parks and Recreation Department | 1100000 USD/ea (2024) | high | https://oregon.gov/oprd/CAC/Documents/2024-11-8d.pdf
specialty-residential/rv-park-resort.json#e17 | Bid Tabulation - Campground Development Phase II, Comfort Station - Rebid, Palisades State Park, GFP Project No. Pali23Oa | South Dakota Department of Game, Fish and Parks | 705540 USD/ea (2023) | high | https://gfp.sd.gov/UserDocs/nav/Bid_Tab_Comfort_Station_Rebid.pdf
specialty-residential/rv-park-resort.json#e18 | Table Rock State Park - Campground Upgrade Project (revenue bond project sheet) | Missouri State Parks (Missouri DNR) | 0.114 pct (2020) | high | https://web.archive.org/web/2022id_/https://mostateparks.com/sites/mostateparks/files/table-rock-campground-project.pdf
specialty-residential/rv-park-resort.json#e19 | Lake of the Ozarks State Park - Campground Upgrade Project (revenue bond project sheet) | Missouri State Parks (Missouri DNR) | 0.15 pct (2020) | high | https://web.archive.org/web/2022id_/https://mostateparks.com/sites/mostateparks/files/LOSP-campground-project.pdf
specialty-residential/rv-park-resort.json#e2 | St. Francois State Park - Campground Upgrade Project (revenue bond project sheet) | Missouri State Parks (Missouri DNR) | 65780 USD/site (2020) | high | https://web.archive.org/web/2022id_/https://mostateparks.com/sites/mostateparks/files/st-francois-campground-project.pdf
specialty-residential/rv-park-resort.json#e21 | RV Park construction in West TD could move forward with $1 million state grant | Columbia Community Connection | 39269 USD/site (2026) | low | https://columbiacommunityconnection.com/the-dalles/rv-park-construction-in-west-td-could-move-forward-with-1-million-state-grant
specialty-residential/rv-park-resort.json#e3 | Table Rock State Park - Campground Upgrade Project (revenue bond project sheet) | Missouri State Parks (Missouri DNR) | 67472 USD/site (2020) | high | https://web.archive.org/web/2022id_/https://mostateparks.com/sites/mostateparks/files/table-rock-campground-project.pdf
specialty-residential/rv-park-resort.json#e4 | Long Branch State Park - Campground Upgrade Project (revenue bond project sheet) | Missouri State Parks (Missouri DNR) | 94445 USD/site (2020) | high | https://web.archive.org/web/2022id_/https://mostateparks.com/sites/mostateparks/files/long-branch-campground-project.pdf
specialty-residential/rv-park-resort.json#e5 | Roaring River State Park - Campground Upgrade Project (revenue bond project sheet) | Missouri State Parks (Missouri DNR) | 49768 USD/site (2020) | medium | https://web.archive.org/web/2022id_/https://mostateparks.com/sites/mostateparks/files/RRSP-campground-project.pdf
specialty-residential/rv-park-resort.json#e6 | Lake of the Ozarks State Park - Campground Upgrade Project (revenue bond project sheet) | Missouri State Parks (Missouri DNR) | 55000 USD/site (2020) | high | https://web.archive.org/web/2022id_/https://mostateparks.com/sites/mostateparks/files/LOSP-campground-project.pdf
specialty-residential/rv-park-resort.json#e7 | Division of Facilities Construction and Management 22223510 - Bud Mahas Construction, Inc. ¦ Govly | Govly (public award record of Utah DFCM) | 112037 USD/site (2022) | medium | https://app.govly.com/public/awards/e357f38dba36a5dcac9434618dbba1fb
specialty-residential/rv-park-resort.json#e8 | How much does it cost to build a campground or RV park? | Outdoor Hospitality Weekly (Substack) | 30000–40000 USD/site (2024) | medium | https://ohweekly.substack.com/p/how-much-does-it-cost-to-build-a
specialty-residential/rv-park-resort.json#e9 | How much does it cost to build a campground or RV park? | Outdoor Hospitality Weekly (Substack) | 4000 USD/site (2024) | low | https://ohweekly.substack.com/p/how-much-does-it-cost-to-build-a